dated [ ]

[ Places for People Group]

and

[		]

JCT Design and Build contract (2016 edition)

| relating to [ ] Trowers & Hamlins LLP 55 Princess Street Manchester M2 4EW t +44 (0)161 838 2000 f +44 (0)161 838 2001 www.trowers.com | 1 |
| --- | --- |
| draft () dated [ ] |  |

Agreement

dated [            ]

Parties

[ Places for People Group                                               ] (registration number [  ]) [of] [whose registered office is at] [                                                     ] (the Employer) and

[                                                   ] (registration number [      ]) [of] [whose registered office is at] [                                                      ] (the Contractor)

Recitals

| - First | - The Employer wishes to have the design and construction of [ ] carried out at [ ] (the Works) in accordance with the conditions (comprising the clauses set out in sections 1 to 9 together with and including schedules 1 to 7 inclusive) annexed to the JCT Design and Build Contract (2016 edition) subject to the amendments and insertions set out in Appendix 1 to this Agreement (hereinafter together called the Conditions) and the Employer has supplied to the Contractor documents showing and describing or otherwise stating his requirements (the Employer's Requirements). |
| --- | --- |
| - Second | - In response to the Employer's Requirements the Contractor has supplied to the Employer: - documents showing and describing the Contractor's proposals for the design and construction of the Works (the Contractor's Proposals); and - an analysis of the Contract Sum (the Contract Sum Analysis). |
| - Third | - The Contractor has checked the Employer's Requirements and confirms: - the Contractor's Proposals meet the Employer's Requirements and there is no discrepancy within and/or between the two documents; and - the Contractor shall be fully responsible in all respects for the design of the Works (whether contained in the Employer's Requirements or the Contractor's Proposals) and design development, selection of goods and materials and satisfaction of performance specifications. |
| - Fourth | - For the purposes of the Construction Industry Scheme (CIS) under the Finance Act 2004 the status of the Employer is, as at the Base Date, that stated in the Contract Particulars. |
| - Fifth | - [The division of the Works into Sections is shown in the Employer's Requirements or in such other documents as are identified in the Contract Particulars.] [Not applicable.] |
| - Sixth | - Where so stated in the Contract Particulars this Contract is supplemented by the Framework Agreement identified in those particulars. |
| - Seventh | - Whether any of the Supplemental Provisions 1-10 apply is stated in the Contract Particulars. |

Articles

Now it is hereby agreed as follows:

| Article 1 | Contractor's obligations The Contractor shall carry out and complete the design for the Works and carry out and complete the construction of the Works in accordance with the Contract Documents. |
| --- | --- |
| Article 2 | Contract Sum The Employer shall pay the Contractor at the times and in the manner specified in the Conditions the VAT exclusive sum of [ ] pounds (£[ ]) (the Contract Sum) or such other sum as becomes payable under the Contract. |
| Article 3 | Employer's Agent For the purposes of the Contract the Employer's Agent is [ ] of [ ] or such other person as the Employer nominates in his place. Save to the extent that the Employer may otherwise specify by written notice to the Contractor the Employer's Agent shall have full authority to receive and issue applications, consents, instructions, notices, requests or statements and otherwise to act for the Employer under any of the Conditions. Notwithstanding the appointment of the Employer's Agent the Employer shall retain authority to issue comments, instructions, requests and notices from time to time for the purposes of this Contract. |
| Article 4 | Employer's Requirements and Contractor's Proposals The Employer's Requirements, the Contractor's Proposals and the Contract Sum Analysis are those referred to in the Contract Particulars (except to the extent that the Contractor's Proposals are developed and completed after the date of this Contract). |
| Article 5 | Principal Designer The Principal Designer for the purposes of the CDM Regulations is the Contractor (or) [ ] of [ ] or such replacement as the Employer at any time appoints to fulfil that role. |
| Article 6 | Principal Contractor The Principal Contractor for the purposes of the CDM Regulations is the Contractor (or) [ ] of [ ] or such replacement as the Employer appoints at any time to fulfil that role. [The Contractor warrants to the Employer that he has the necessary skills, knowledge and experience to undertake the role of Principal Contractor as defined in the CDM Regulations and has sufficient resources and will allocate those resources to the fulfilment of his duties as Principal Contractor.] |
| Article 7 | Adjudication If any dispute or difference arises under this Contract either Party may refer it to adjudication in accordance with clause 9. |
| Article 8 | Legal proceedings Subject to Article 7, the English courts shall have exclusive jurisdiction over any dispute or difference between the Parties which arises out of or in connection with this Contract. |
| Article 9 | Retrospective effect and letters of intent Notwithstanding the date of this Contract it shall have effect as if it had been executed upon the date the Contractor first performed any work (including design enabling, temporary or other preliminary demolition or permanent works) or activities in relation to the Works (whether under [the letter[s] of intent dated [ ],[, pre – construction services agreements dated [ ]]or otherwise) and accordingly the duties and obligations contained in this Contract shall be deemed to have applied to the carrying out of any of those works and/or the Works prior to the date of this Contract. All payments made in respect of works carried out prior to the date of this Contract shall be treated as payments on account of sums due under this Contract. |

Contract Particulars

| Clause | Subject |  |
| --- | --- | --- |
| Fourth Recital and clause 4.5 | Construction Industry Scheme (CIS) | Employer at the Base Date is [not] a 'contractor' for the purposes of the CIS |
| Fifth Recital | Description of Sections (if any) (if not shown or described in the Employer's Requirements, state the reference numbers and dates or other identifiers of documents in which they are shown.) | [ ] [Not used] |
| Sixth Recital | Framework Agreement (if applicable) ( State date, title and parties) | [ ] |
| Seventh Recital and Part 1 of Schedule 2 | Supplemental Provisions – part 1 (Where neither entry against one of the Supplemental Provisions 1 to 3 below is deleted that Supplemental Provision does not apply) |  |
|  | Named Sub-Contractors | Supplemental Provision 1 applies / does not apply |
|  | Valuation of Changes – Contractor's estimates | Supplemental Provision 2 applies / does not apply |
|  | Loss and expense – Contractor's estimates | Supplemental Provision 3 applies / does not apply |
| Seventh Recital and Part 2 of Schedule 2 | Supplemental Provisions – Part 2 (Where neither entry against one of the Supplemental Provisions 4 to 10 below is deleted that Supplemental Provision applies) |  |
|  | Acceleration Quotation | Supplemental Provision 4 applies / does not apply |
|  | Collaborative working | Supplemental Provision 5 applies / does not apply |
|  | Health and safety | Supplemental Provision 6 applies / does not apply |
|  | Cost savings and value improvements | Supplemental Provision 7 applies / does not apply |
|  | Sustainable development and environmental considerations | Supplemental Provision 8 applies / does not apply |
|  | Performance indicators and monitoring | Supplemental Provision 9 applies / does not apply |
|  | Notification and negotiation of disputes | Supplemental Provision 10 applies / does not apply |
|  | Where Supplemental Provision 10 applies, the respective nominees of the Parties are | Employer's nominee: [ ] Contractor's nominee: [ ] or such replacement as each Party may notify to the other from time to time |
| Article 4 | Employer's Requirements (State the reference numbers and dates or other identifiers of the relevant documents.) | [ ] |
| Article 4 | Contractor's Proposals (State the reference numbers and dates or other identifiers of the relevant documents.) | [ ] |
| Article 4 | Contract Sum Analysis (State the reference numbers and dates or other identifiers of the relevant documents.) | [ ] |
| 1.1 | Base Date | [ ] |
| 1.1 | BIM Protocol (where applicable) (State title, edition, date or other identifiers of relevant documents) | [ ] |
| 1.1 or | Date for Completion of the Works (where completion by Sections does not apply) | [ ] |
| 1.1 | Sections: Dates for Completion of Sections | Section [ ] : [ ] Section [ ] : [ ] Section [ ] : [ ] |
| 1.1 | Novated Consultants | [ ] [ ] |
| 1.7 | Addresses for service of notices by the Parties (if none is stated, the address in each case subject to clause 1.7.3, shall be that shown at the commencement of the Agreement.) | Employer [ ] Contractor [ ] |
| 2.1.5.1.4 | Prohibited materials | Materials specifically prohibited are [detailed in [ ]] [ ] |
| 2.3 or | Date of Possession of the site (Where possession by Sections does not apply) | [ ] |
| 2.3 | Sections: Dates of Possession of Sections | Section [ ] : [ ] Section [ ] : [ ] Section [ ] : [ ] |
| 2.4 or | Deferment of possession of the site (Where possession by Sections does not apply) | [Clause 2.4 does not apply] [Clause 2.4 applies and the maximum period of deferment is [ ]] |
| 2.4 | Sections: deferment of possession of Sections | [Clause 2.4 does not apply] [Clause 2.4 applies and the maximum period of deferment is: Section [ ] : [ ] Section [ ] : [ ] Section [ ] : [ ]] |
| 2.29.2 or | Liquidated damages (Where completion by Sections does not apply) | at the rate of £[ ] per [ ] |
| 2.29.2 | Sections: rate of liquidated damages for each Section | Section [ ] : £[ ] per [ ] Section [ ] : £[ ] per [ ] Section [ ] : £[ ] per [ ] |
| 2.34 | Sections: Section Sums | Section [ ] : £ Section [ ] : £ Section [ ] : £ |
| 2.35 or | Rectification Period ( Where completion by Sections does not apply) | [ ] months from the date of practical completion of the Works (or twelve months if no other period is stated) |
| 2.35 | Sections: Rectification Periods | Section [ ] : [ ] months Section [ ] : [ ] months Section [ ] : [ ] months from the date of practical completion of each Section (or twelve months if no other period is stated) |
| 4.6 | Advance payment | Clause 4.6 does [not] apply [If applicable the advance payment will be [£[ ]] [[ ] % of the Contract Sum] and will be paid to the Contractor on [ ]. It will be reimbursed to the Employer in the following amount(s) and at the following time(s): [ ]] |
| 4.6 | Advance Payment Bond (where an advance payment is to be made, an advance payment bond is required unless stated that it is not required) | An advance payment is [not] required |
| 4.7.1 | Method of Payment – alternatives (if no Alternative is selected, Alternative B applies) | By stages in accordance with Alternative A (clause 4.12) / periodically in accordance with Alternative B (clause 4.13) |
|  | Alternative A: Stage Payments | The stages are [set out on a separate sheet attached] [as follows:] |
|  | Stages (insert brief description) [ ] [ ] | Cumulative total £[ ] £[ ] |
| 4.7.2 | Interim Payments - Interim Valuation Date (the dates apply for each Alternative: if no date is stated, the first Interim Valuation Date is one month after the Date of Possession) | The first Interim Valuation Date is [ ] and thereafter the same date in each month or the nearest Business Day in that month |
| [4.15.4 | Listed Items – uniquely identified (Delete the entry if no bond is required) | For uniquely identified Listed Items a bond in respect of payment for such items is required for £[ ]] |
| [4.15.5 | Listed Items – not uniquely identified (Delete the entry if clause 4.15.5 does not apply) | For Listed Items that are not uniquely identified a bond in respect of payment for such items is required for £[ ]] |
| 4.17 | Contractor's Retention Bond (Not applicable unless stated to apply with relevant particulars given below.) | Clause 4.17 applies / does not apply |
|  |  | If clause 4.17 applies the maximum aggregate sum for the purposes of clause 2 of the bond is £ [ ]; and for the purposes of clause 6.3 of the bond the expiry date shall be [ ] |
| 4.18.1 | Retention Percentage (The percentage is 3 per cent unless a different rate is stated; if no retention is required, insert 'Nil' or '0') | [ ] per cent |
| 5.5 | Daywork | The Percentage Additions to each section of the prime cost or, if they apply in respect of labour, the All Inclusive Rates are set out in the following documents: [ ] |
| 6.4.1 | Contractor's Public Liability insurance: injury to persons or property – the required level of cover is not less than | £[ 10,000,000 ] for any one occurrence or series of occurrences arising out of one event |
| 6.5.1 | Insurance – liability of Employer | Minimum amount of indemnity for any one occurrence or series of occurrences arising out of one event £[ ] |
| 6.7 and Schedule 3 | Works insurance – Insurance Option applicable | Schedule 3: Insurance Option A / B / C applies |
|  | Percentage to cover professional fees (If no other percentage is stated, it shall be 15 per cent.) | [ ] per cent |
|  | Where Insurance Option A applies and cover is to be provided under the Contractor's annual policy (paragraph A.2) the annual policy renewal date is (as supplied by the Contractor) | [ ] |
|  | Where Insurance Option C applies, paragraph C.1 (unless otherwise stated, paragraph C.1 applies. If it is not to apply, state the reference number and date or other identifier of the replacement document(s)) | Applies/is replaced by the provisions of the following documents [ ] (the C.1 Replacement Schedule) |
| 6.10 and Schedule 3 | Terrorism Cover – details of the required cover (unless otherwise stated, Pool Re Cover is required) | Are set out in the following document(s): |
| 6.15 | Professional indemnity insurance |  |
|  | Level of cover | Amount of indemnity required [is for each and every claim] [relates to claims or series of claims arising out of one event] / [is the aggregate amount for each year of insurance] and is £[ ] ([ ] pounds) |
|  | Cover for pollution/contamination claims (if no amount is stated, such cover shall not be required; unless otherwise stated the required limit of indemnity is an annual aggregate amount) | is required with an indemnity limit of £[ ] / is not required |
| 6.17 | Joint Fire Code | The Joint Fire Code does [not] apply |
|  | If the Joint Fire Code applies, state whether the insurer under Insurance Option A, B or C (paragraph C.2) has specified that the Works are a 'Large Project': | [Yes] [No] Error: Reference source not found |
| 6.20 | Joint Fire Code – amendments/revisions (The cost shall be borne by the Contractor unless otherwise stated.) | The cost, if any, of compliance with amendment(s) or revisions(s) to the Joint Fire Code shall be borne by the [Employer] [Contractor] |
| 7.3.1 | Performance bond or guarantee from bank or other approved surety (If this entry is not completed or the required form is not specified, a performance bond or guarantee is not required) | *is required / is not required |
|  | The required form of the bond or guarantee is set out in | [ ] |
|  | Initial value | [ ] per cent of the Contract Sum |
|  | Period of validity – if not specified in the required form, the expiry date of the performance bond or guarantee is to be (if no entry is selected, the date shall be the date of practical completion of the Works) | *[the date of practical completion of the Works / * 2 weeks after the date of expiry of the Rectification Period for the Works / * the date for issue of the Notice of Completion of Making Good for the Works] |
|  | Reduction in value – if not specified in the required form and if expiring later than the date of practical completion of the Works, the percentage reduction in the initial value on that date is (if no other percentage is stated, it shall be 50 percent) | [[ ] per cent]/ [Not applicable] |
| 7.3.2 | Guarantee from the Contractor's parent company | * is required / is not required |
|  | Parent company's name and registration number | [ ] |
|  | The required form of the guarantee is set out in | [ ] |
| 7.4 | Third Party Rights and Collateral Warranties – details of the requirements for the grant by the Contractor and Sub-contractors of P&T Rights, Funder Rights and/or (in the case of Sub-contractors) Employer Rights in respect of the Works, or for the provision of collateral warranties ("Rights Particulars") are set out in | See clauses 7A to 7E (inclusive) |
| 8.9.2 | Period of suspension (If none is stated, the period is 2 months.) | [ ] |
| 8.11.1.1 to 8.11.1.6 | Period of suspension (If none is stated, the period is 2 months.) | [ ] |
| 9.2.1 | Adjudication | The Adjudicator is [ ] |
|  | Nominating body – where no Adjudicator is named or where the named Adjudicator is unwilling or unable to act (whenever that is established) (Where an Adjudicator is not named and a nominating body has not been selected, the nominating body shall be one of the bodies listed opposite selected by the Party requiring the reference to adjudication.) | Royal Institute of British Architects The Royal Institution of Chartered Surveyors constructionadjudicators.com Association of Independent Construction Adjudicators Chartered Institute of Arbitrators |

This Agreement has been executed as a deed and is delivered and takes effect on the date stated at the beginning of it

[insert appropriate execution blocks]

Appendix 1

Amendments

Section 1 – definitions and interpretation

Clause 1.1

Delete the definitions of Agreement, Conditions, Contractor's Design Documents, Employer, Employer Rights, Finance Agreement, Funder, Funder Rights, P&T Rights, Purchaser, Statutory Requirements, Tenant, VAT and Works

Insert:

"Agreement : the Agreement to which these Conditions are annexed including its Recitals, Articles and Contract Particulars and appendices 1 to [9].

[Anti-corruption Policy : the Employer's [ethics, anti-bribery and anti-corruption policies] [dated [        ] reference [          ]] copies of which have been provided to the Contractor] [copies of which are attached at appendix [9]] as may be amended from time to time and notified to the Contractor.]

[Anti-slavery Policy : the Employer's anti-slavery policy attached at Annex [ ],[ as amended by notification to the Contractor from time to time ].]

Associated Person : a person (including an employee, agent or subsidiary) who performs services for or on the Contractor's behalf.

Best Environmental Practice : best practice generally followed by [design and build contractors] skilled and experienced in the remediation and redevelopment of contaminated sites and shall be deemed to include (as a minimum) compliance with all Environmental Laws.

Bribery Act : the Bribery Act 2010.

Conditions : the conditions as defined in the First Recital in the Agreement.

Consents : the planning permissions referred to in the Employer's Requirements or any other planning permissions relating to the Works, approval of reserved matters and all details pursuant thereto, building regulation approval, fire officer approval and any other permissions, approvals, certificates and licences that may be necessary pursuant to the Statutory Requirements or otherwise to the carrying out of the Works and if they are destroyed or damaged, the reinstatement of the Works.

Contractor's Design Documents : all drawings, plans, models, specifications, reports, calculations, charts, diagrams, sketches (including without limitation any such items retained on or in any computer software or other electronic medium) and other works prepared conceived or developed by or on behalf of the Contractor (including by any of the [Novated Consultants,] Sub-Consultants and Sub-Contractors) in the course of or as a result of carrying out the Works whether in existence or to be made or produced and including all amendments, additions and all designs, ideas, concepts, and inventions contained in them.

Corrupt Activity : [extortion, fraud, deception, collusion, cartels, abuse of power, embezzlement, trading in influence, money-laundering or any similar activity] [bribery and/or corruption] including, without limitation, any activity, practice or conduct which would or could constitute an offence under sections 1, 2 or 6 Bribery Act [if such practice or conduct had been carried out in the United Kingdom] and/or would constitute a UK or foreign tax evasion offence or UK or foreign tax evasion facilitation offence under sections 45 and 46 Criminal Finances Act whether in connection with the Works or otherwise.

Criminal Finances Act : the Criminal Finances Act 2017.

Data Protection Legislation :  all applicable data protection and privacy legislation in force from time to time in the UK including but not limited to the General Data Protection Regulation ((EU) 2016/679) (the GDPR); the UK GDPR (as such term is defined in the Data Protection, Privacy and Electronic Communications (Amendments etc.) (EU Exit) Regulations 2019) (such legislation being referred to in this Agreement as the UK GDPR), the Data Protection Act 2018; the Privacy and Electronic Communications Directive 2002/58/EC (as updated by Directive 2009/136/EC) and the Privacy and Electronic Communications Regulations 2003 (SI 2003/2426), along with any associated guidance and Codes of Practice, in each case as may be amended, updated or supplemented from time to time.

Data Subject's Rights : any rights of individuals under the Data Protection Legislation.

Data Controller, Data Subjects, Personal Data and Processing shall have the meaning as provided in the Data Protection Legislation.

[Deed of Novation : the deed or deeds of novation in the form set out in [Appendix 4 to the Agreement.]

Employer : the person named as Employer in the Agreement and their successors in title and assigns.

Employer Rights: the rights in favour of the Employer to be granted by Sub-contractors in accordance with the Rights Particulars either by way of third party rights or by collateral warranties.

Environment : all and any of the following media being water, air or land (wherever situated) as well as any eco-systems; organisms, including (without limitation) humans, and their property, including natural and man-made structures.

Environmental Laws : all rules of common law, principles of equity and rules of any court or other tribunal of competent jurisdiction, all statutes, standards or codes of practice that have the force of law, all notices, directions, impositions or requirements of any competent authority relating to the protection of human health and safety, the protection of property and proprietary rights or the protection of the Environment or the generation, transportation, storage, use, treatment or disposal of Hazardous Substances.

[Environmental Report : the report dated [		] (reference [	]) prepared by [	] in relation to [			].]

Funder : a person (whether acting for himself and/or where leading for a syndicate of persons as agent and trustee for such persons) who is providing or shall provide interim or other finance for the carrying out of the Works itself and / or for the acquisition of the site.

[Funder Rights : the rights in favour of a Funder set out in Schedule 5A [ or those to be granted by Sub-contractors in accordance with the Rights Particulars].]

Funder's Surveyor : such employee of any Funder or such surveyor or firm of surveyors appointed by any Funder as may be notified from time to time to the Contractor and "Funder's Surveyors" shall be construed accordingly.

Group Company : any subsidiary or holding company of the Employer or another subsidiary or holding company of such company as subsidiary and holding company are defined in section 1159 Companies Act 2006.

Hazardous Substance : means waste (as defined in the Environmental Protection Act 1990) and any substance whatsoever in any form (whether alone or in combination with any other substance) which is capable of causing harm to man or to any living organism supported by the Environment or of damaging the Environment or public health or welfare or the presence of which would be a breach of any Environmental Law.

HMRC : means HM Revenue & Customs.

[Human Trafficking Statement : a statement made in accordance with section 54 of the Modern Slavery Act 2015 together with any guidance issued by the Secretary of State.]

[Modern Slavery Legislation : the legislation referred to in section 54 of the Modern Slavery Act 2015.]

Moral Rights : moral rights under Chapter IV Part 1 Copyright Designs and Patents Act 1988.

[Nominating Notice : a written notice in the form set out in Appendix 8 to the Agreement which may be issued for and on behalf of the Employer.]

[Novated Consultants : those consultants to be novated to the Contractor pursuant to clause 3.17 and identified in the Contract Particulars and reference to a Novated Consultant means any one of them.]

Order : means the Value Added Tax (Section 55A) (Specified Services and Excepted Supplies) Order 2019 (SI 2019 No. 892).

[P&T Rights : the rights in favour of a Purchaser or a Tenant set out in Schedule 5 [ or those to be granted by Sub-contractors in accordance with the Rights Particulars].]

Purchaser : a person who has acquired or has agreed to acquire or may later acquire or agree to acquire a freehold or long leasehold interest in the whole or any part of the site (and/or any premises constructed or to be constructed on the site) and "Purchasers" shall be construed accordingly.

Purchaser's Surveyor : such employee of any Purchaser or such surveyor or firm of surveyors appointed by any Purchaser, as may be notified from time to time to the Contractor and "Purchasers' Surveyors" shall be construed accordingly.

Reverse Charge : means, in relation to a supply, that under section 55A(6) of the Value Added Tax Act 1994 it is for the recipient, on the supplier's behalf, to account for and pay VAT on the supply and not for the supplier.

Statutory Agreements : an agreement pursuant to section 38 and/or 278 Highways Act 1980 and/or an agreement pursuant to section 104 Water Industry Act 1991 and/or an agreement pursuant to section 106 Town and Country Planning Act 1990 and/or section III Local Government Act 1972.

Statutory Requirements : any Acts of Parliament and any instruments, rules, orders, regulations notices, directions, bye-laws, permissions and plans for the time being made under or deriving validity from them (including any which although they have not yet come into effect whether in whole or in part will or may do so as to affect the Works and/or the buildings and structures the subject of the Works once built), any retained EU legislation legally enforceable in England and Wales, and any rules, regulations, building regulations, orders, bye-laws or codes of practice of any local or other competent authority or of any statutory undertaker which has jurisdiction with regard to the Works or with whose systems the same are or will be connected including Development Control Requirements.

Sub-Consultants : consultants engaged or to be engaged by the Contractor (including any replacement consultants) in relation to the Works to provide design or other professional services [in addition to the Novated Consultants].

Sub-Contractors : those sub-contractors engaged or to be engaged (including any replacement sub-contractors) to carry out the following elements of the Works: [curtain walling; electrical installation; escalators; ground floor slab; ground improvements; lifts; mechanical installation; piling; pre-cast concrete; raised floors; roof and wall cladding; steelwork; structural frame; windows and external doors] together with any other sub-contractor carrying out the design of a material element of the Works and reference to a "Sub-Contractor" means any one of them.

Supply : means a supply made for VAT purposes under or in connection with this Agreement by the Contractor and "Supplies" shall be construed accordingly.

Tenant : a person who has taken or has agreed to take or may later take or agree to take a lease of the whole or any part of the site (and/or any premises constructed or to be constructed on the site) and "Tenants" shall be construed accordingly.

Tenant's Surveyor : such employee of any Tenant or such surveyor or firm of surveyors appointed by any Tenant as may be notified from time to time to the Contractor and "Tenants' Surveyors" shall be construed accordingly.

Third Party Agreements : any and all agreements relating to or affecting the Works or the completed Works (including the execution of the Works and their design) or any part of the Works which have been entered into by the Employer and/or any Group Company before the date of this Contract and disclosed to the Contractor on or before the date of this Contract including any agreements referred to as such in the Employer's Requirements.

VAT : means value added tax chargeable under the Value Added Tax Act 1994 and any similar or replacement tax.

Works : comprises the design and construction of [             ] including all pre construction work, works for the provision of and diversion of services and all ancillary works carried out on or about the site and briefly described in the First Recital and referred to in the Employer's Requirements and the Contractor's Proposals and including any changes made to those works in accordance with this Contract (whether carried out before or after the date of this Contract)."

Clause 1.3

Delete clause 1.3 and insert:

"1.3.1 	The Agreement and these Conditions are to be read as a whole.  Subject to clause 2.14 	in the event of any inconsistency occurring between Appendix 1 to the Agreement, the 	Agreement, the Contract Particulars, the clauses set out in sections 1 to 9 of 	the printed JCT Design & Build Contract 2016 edition and the schedules 	thereto, the 	Supplemental Provisions, the Employer's Requirements, the Contractor's Proposals and	the Contract Sum Analysis, the contents of the document appearing earlier in the 	preceding order shall prevail over any document appearing later in the preceding order.

1.3.2	This Contract represents the entire agreement between the Employer and the 	Contractor 	and supersedes any previous agreement or understanding between them in 	relation to the Works (including, but not limited to any letter of intent or pre-construction 	services agreement). In entering into this Contract, the Contractor does not rely upon 	any antecedent or collateral representation or promise made by or on behalf of the 	Employer, and (in the absence of fraud) the Contractor shall not have any claim, right or 	remedy (including any claim for rescission or damages for innocent or negligent 	misrepresentation) arising out of any such antecedent or collateral representation or 	promise."

Clause 1.6

Delete clause 1.6 and insert:

"[Other than such rights of Purchasers and/or Tenants as take effect pursuant to clause 7A and/or such rights of Funders as take effect pursuant to clause 7B nothing] [Nothing] in this Contract confers or purports to confer any rights on any person pursuant to the Contracts (Rights of Third Parties) Act 1999."

Clause 1.8.1.1

Delete clause 1.8.1.1 and insert "Not used."

Clause 1.9

In line 1 delete "Save as stated in clause 1.8 no" and insert "No"

Clause 1.11

- Delete clause 1.11 and insert:

"1.11.1	The Parties agree that this Contract and any dispute or claim arising out of or in connection with this Contract, its negotiation or subject matter or any non-contractual obligation arising in connection with the foregoing, shall be governed by and construed in accordance with English law.

1.11.2	Each of the Parties irrevocably agrees to submit to the exclusive jurisdiction of the courts of England and Wales in relation to any claim or matter arising out of or in connection with this Contract, its negotiation or subject matter, or any non-contractual obligation arising in connection with the foregoing."

Clause 1.12

Insert new clause 1.12:

"All references to arbitration, fluctuations and fluctuation provisions in this Contract (including the relevant definitions in clause 1.1) shall be deemed to be deleted."

Clause 1.13

Insert new clause 1.13:

"Liability period

Neither Party shall commence any action or proceedings against the other under this Contract after 12 years from the date of practical completion of the Works and any adjudicator's decision under clause 9.2 shall be finally binding on them unless either Party has referred that dispute for final determination by legal proceedings, or has commenced any action or proceedings to recover any overpayment to which the decision has led, before that date."

Section 2 – Carrying out the Works

Clause 2.1.1

In line 1 after "workmanlike manner" insert ", in accordance with good building practice"

In line 3 after "for that purpose shall" insert "carry out and"

Clause 2.1.2

Delete clause 2.1.2 and insert "Not used."

Clause 2.1.3

Insert at the start of the clause:

"The Contractor shall be responsible for obtaining all Consents to enable the Works to be completed in accordance with the Employer's Requirements."

At the end of the clause before "." insert "and when requested to do so by the Employer the Contractor shall provide the Employer with evidence that he has complied with all Statutory Requirements and given all notices required by the Statutory Requirements"

Clause 2.1.5

Insert new clause 2.1.5:

"2.1.5.1	The Contractor warrants that it has not and shall not specify, use, authorise, cause or allow to be used in the Works any products or materials which:

2.1.5.1.1	do not conform with UK Designated Standards (where appropriate) or Codes of Practice (or where no such standard exists do not conform with a British Board of Agrément Certificate); and/or

2.1.5.1.2	are generally known in the construction industry to be deleterious, in the particular circumstances in which they are specified for use, to health and safety and/or the durability of buildings or structures; and/or

2.1.5.1.3	do not comply with the guidance set out in "Good Practice in the Selection of Construction Materials 2011" published by the British Council for Offices; and/or

2.1.5.1.4		are specifically prohibited by this Contract.

2.1.5.2	The Contractor will immediately notify the Employer if it becomes aware of any proposed or actual specification and/or use in the Works of any products and/or materials which do not comply with clause 2.1.5.1."

Clause 2.1.6

Insert new clause 2.1.6:

"Where the Employer's authorisation or completion of documentation in respect of the Statutory Requirements is required the Contractor shall furnish the relevant documentation to the Employer and permit the Employer a period of 10 Business Days to authorise or complete it."

[Clause 2.1.7

Insert new clause 2.1.7:

"In performing its obligations under this Contract, the Contractor shall [, and shall ensure that each of its sub-contractors shall,] comply with the Modern Slavery Legislation [ and the Anti-Slavery Policy]].

Clause 2.2.1

Delete clause 2.2.1 and insert:

"All materials, goods and workmanship used in the execution of the Works shall be of such kinds and of such quality as are necessary to enable the Contractor to comply with his obligations under this Contract."

Clause 2.2.2

Delete clause 2.2.2 and insert:

"The Contractor shall not make any substitution for any materials, goods or workmanship specified or described in the Employer's Requirements or (if not specified or described in the Employer's Requirements) as set out in the Contractor's Proposals or in the specifications revised and returned to the Contractor by the Employer in accordance with the  Design Submission Procedure  without the prior consent (not to be unreasonably withheld or delayed) in writing of the Employer."

Clause 2.2.4

Delete "at the Employer's request provide him" and insert "provide the Employer"

Clause 2.2.6

Insert new clause 2.2.6:

- "The Contractor shall carry out and complete the Works in accordance with Best Environmental Practice [, the recommendations of the Environmental Report] and Environmental Laws."

[Clause 2.2.7

Insert new clause 2.2.7:

"The Contractor shall:

- 2.2.7.1	carry out such further environmental investigation works as necessary [and specifically such work as recommended in the Environmental Report];

- 2.2.7.2	provide the Employer with a copy of any report and/or recommendations arising from the carrying out of such further investigations pursuant to clause 2.2.7.1;

- 2.2.7.3	comply with any recommendations arising from the further investigations pursuant to clause 2.2.7.1."]

Clause 2.2.8

Insert new clause 2.2.8:

"The Contractor shall be liable for and shall indemnify and keep indemnified the Employer against any liability, damage, loss, expense, cost, claim or proceedings arising before on or after the date of this Contract in respect of any act or omission on the Contractor's part which results, whether directly or indirectly, in damage to the Environment and/or a breach of or failure by the Contractor to comply with its obligations under Environmental Laws insofar as such loss, injury or damage arises out of or in the course of or by reason of the carrying out the Works and to the extent that the same is due (wholly or partly) to any act or omission of the Contractor, any of its sub-contractors or their respective employees, servants or agents employed or engaged upon or in connection with the Works or any part or parts of the Works."

Clause 2.7.1

Delete clause 2.7.1 and insert "The Contract Documents shall be prepared in duplicate and once completed one set shall remain in the custody of the Employer and the other set shall be returned to the Contractor."

Clause 2.7.2

In lines 3-4 delete "one copy, certified on behalf of the Employer, of the Contract Documents together with"

Clause 2.7.3

In line 1 after "Employer's Agent" insert "and/or any Funder's Surveyor and/or any Tenant's Surveyor and/or any Purchaser's Surveyor"

Clause 2.7.4

Delete clause 2.7.4 and insert:

"The Contractor shall not (and shall procure that the Contractor's Persons shall not) without prior written approval of the Employer take or permit to be taken any photos of the Works or any part or parts of the Works for use in any publicity or advertising or publish alone or in conjunction with any other person any articles, photos or other illustrations relating to the Works or any part or parts of the Works nor shall he impart to any publication, journal or newspaper or any radio or TV programme any information relating to the Works."

Clause 2.7.6

Insert new clause 2.7.6:

"2.7.6.1	The Contractor shall not (and shall procure that the Sub-Consultants[,] [and/or] any sub-contractors [and/or the Novated Consultants] shall not) disclose to any person or publish or make any statement concerning this Contract or the Works or any matters arising from or relating to the Contract or the Works directly or indirectly without the prior written authority of the Employer during the Works or at any time thereafter (except as may be required by law or in order to properly perform its obligations under this Contract (or in the case of Sub-Consultants[,] [and/or] any sub-contractors [and/or the Novated Consultants] as may be required in order to properly perform their obligations under their contracts/terms of engagement in relation to the Works)).

2.7.6.2	Both the Employer and the Contractor shall keep confidential and shall not without the other's written consent disclose to any third party any trade or business secrets or similar confidential information supplied by the other Party except as shall be absolutely necessary for the proper performance of this Contract.

2.7.6.3	The Contractor shall not:

2.7.6.3.1	use the Contractor's Design Documents for any purpose whatsoever other than in the carrying out of the Works under this Contract; or

2.7.6.3.2	without the Employer's consent use the Contractor's Design Documents to design any other project or development which is of similar design appearance or concept to the Works.

2.7.6.4	The Contractor shall provide (without charge to the Employer) to any third party acquiring an interest in the Works, the site and/or the property or properties comprising the Works or any part or parts of the Works upon request by the Employer such documents and information as may be reasonably requested to demonstrate the Contractor's compliance with this Contract.

2.7.6.5	The provisions of clause 2.7.4, 2.7.5 and this clause 2.7.6 shall continue in full force and effect notwithstanding any suspension or determination of the employment of the Contractor and/or the determination of this Contract."

Clause 2.9

Delete clause 2.9 and insert:

"The Contractor shall be deemed to have satisfied itself as to the extent of the boundaries comprising the site and notwithstanding any other provision of this Contract no matter arising from the extent of the boundaries of the site shall give rise to any adjustment of the Contract Sum or any extension of time (whether under clause 2.25 or otherwise) or to any entitlement on the part of the Contractor to loss and expense (whether under clause 4.20 or otherwise) or to any entitlement on the part of the Contractor to determine his employment under this Contract (whether under clauses 8.9 to 8.12 or otherwise)."

Clause 2.10.1

In lines 2 – 3 delete "and such instruction shall be treated as a Change" and insert "and the Contractor shall comply with such instruction without cost to the Employer and the Contractor shall not be entitled to an extension of time"

Clause 2.11

Delete clause 2.11 and insert "Not used."

Clause 2.12

Delete clause 2.12 and insert "Not used."

Clause 2.13

Delete clause 2.13 and insert "Not used."

Clause 2.14

Delete clause 2.14 and insert:

"2.14.1	Where there is a discrepancy within the Contractor's Proposals or within the Employer's Requirements or between the Employer's Requirements and the Contractor's Proposals and/or any drawings, details, documents or information submitted in accordance with clause 2.8 and Schedule 1 the Contractor shall notify the Employer of his proposed amendment to remove the discrepancy; and (subject always to compliance with Statutory Requirements) the Employer shall decide between the discrepant items or otherwise may accept the Contractor's proposed amendment and the Contractor shall be obliged to comply with the decision or acceptance by the Employer without cost to the Employer.

2.14.2	The Contractor accepts entire responsibility for the Employer's Requirements and the Contractor's Proposals and for any mistake inaccuracy or omission in the Employer's Requirements and/or the Contractor's Proposals.  Any mistake, inaccuracy or omission in the Employer's Requirements, the Contractor's Proposals or in any drawings details documents or information referred to in clause 2.8 and schedule 1 shall be corrected by the Contractor without cost to the Employer.

2.14.3	The Contractor shall not have or make any claim for an extension of time under clauses 2.25 and 2.26 or for loss and/or expense under clauses 4.20 and 4.21 and clause 8.9 shall not have effect where and to the extent that the cause of the progress of the Works having been delayed, affected or suspended is due to any such discrepancy, mistake inaccuracy or omission as is referred to in clauses 2.14.1 or 2.14.2 or any failure by the Contractor to provide necessary drawings or documents in due time.

2.14.4	If the Contractor or the Employer finds any such discrepancy as referred to in clause 2.14.1 or any mistake, inaccuracy or omission as referred to in clause 2.14.2 he shall immediately notify the other specifying the discrepancy, mistake, inaccuracy or omission."

Clause 2.15.1

In second sentence delete "entirely at his own cost" and insert "at no additional cost to the Employer" and delete "and the Employer shall note the amendment on the Contract Documents"

Clause 2.15.2.1

In line 1 delete "If" and insert "Subject to clause 2.15.3, if"

Clause 2.15.2.2

In line 1 delete "If" and insert "Subject to clause 2.15.3, if"

In line 5 before "." insert "and provided always that any amendment to the Contractor's Proposals necessary for conformity with Building Regulations or for conformity with any requirement or decision of a building control officer and/or fire officer shall not be treated as a Change"

Clause 2.15.3

Insert new clause 2.15.3:

"The provisions of clause 2.15.2.1 and clause 2.15.2.2 in respect of a change in the Statutory Requirements shall only apply if the change could not reasonably have been foreseen by the Contractor prior to the Base Date."

Clause 2.17

Delete clause 2.17 and heading and insert:

"2.17.1	The Contractor shall (to the extent set out in clause 2.17.2.1 below) be fully responsible in all respects for the design of the Works including but not limited to:

2.17.1.1	any design contained in the Employer's Requirements and for any discrepancy in or divergence between the Employer's Requirements and/or the Contractor's Proposals and/or any drawings, details, documents and other information submitted by the Contractor in accordance with clause 2.8 and Schedule 1;

2.17.1.2	the co-ordination and integration of all design and the interface between design elements for the Works whether carried out by the Contractor or by any other party engaged on the Works and the Contractor shall adopt and take responsibility for any design work in relation to the Works which may be carried out or which may have been carried out by [Novated Consultants (prior to novation),] sub-consultants or sub-contractors or by any other person at the request of the Employer;

2.17.1.3	all aspects of design development, selection of goods and materials and the satisfaction of performance specifications or requirements included or referred to in the Employer's Requirements, the Contractor's Proposals, this Contract or any Change.

2.17.2	Without prejudice to any expressed or implied warranties or conditions or to the generality of clause 2.17.1, the Contractor warrants to the Employer that:

2.17.2.1	the design of the Works (including any design carried out by any design consultant or any sub-contractor with design responsibility or by any other person whether or not employed or engaged by the Contractor) has been and will be carried out using all the reasonable skill and care to be expected of a professionally qualified and competent [designer of the relevant discipline] [design and build contractor] experienced in the carrying out of such work for projects of a similar size, scope, value character and complexity to the Works;

2.17.2.2	the Contractor shall design and construct the Works in compliance with all Consents (including without limitation, the discharge of any reserved matters in planning consents relating to the Works), Statutory Agreements, Statutory Requirements, relevant codes of practice, UK Designated Standards and manufacturers' recommendations and the requirements of the insurers of the Employer (insofar as details have been provided to the Contractor at the date of this Contract)."

Clause 2.21

In second sentence delete "Interim Payment" and insert "Gross Valuation in respect of which the Interim Payment due has been paid or discharged"

Insert at the end of clause 2.21:

"Payment for such goods and materials shall be subject to clause 4 and subject to the Contractor demonstrating to the Employer's satisfaction that:

2.21.1	such materials and goods are intended for inclusion in the Works;

2.21.2	nothing remains to be done to such materials or goods to complete the same up to the point of their inclusion in the Works;

2.21.3	where such materials or goods were ordered from a supplier by the Contractor or a sub-contractor, the contract for their supply is in writing and expressly provides that the property in such goods or materials shall pass unconditionally to the Contractor or sub-contractor (as the case may be) upon their delivery to or placing on or adjacent to the Works;

2.21.4	where such materials or goods were ordered from a supplier by a sub-contractor, the relevant sub-contract is in writing and expressly provides that on the property in such materials or goods passing to the sub-contractor the same shall immediately pass to the Contractor;

2.21.5	where such materials or goods were manufactured or assembled by a sub-contractor, the sub-contract is in writing and expressly provides that the property in such materials or goods shall pass unconditionally to the Contractor upon their delivery to or placing on or adjacent to the Works;

2.21.6	the goods and materials are in accordance with this Contract;

2.21.7	the Contractor provides the Employer with reasonable proof that the property in such materials or goods is vested in him, that he has paid any sums due in respect of such materials or goods and that the relevant conditions set out in clauses 2.21.1 to 2.21.6 have been complied with."

Clause 2.22

In lines 1-2 delete "Interim Payment" and insert "Gross Valuation in respect of which the Interim Payment due has been paid or discharged"

Clause 2.25.1.2

In line 1 after "Section" insert "has been or"

At the end of the clause delete "," and insert ";"

Clause 2.25.1.3

Insert new clause 2.25.1.3:

["and provided that the Contractor has complied with clause 2.25.6] [[and] any delay [caused by an event referred to in clause 2.26.7 to 2.26.12 inclusive] which is concurrent with another delay for which the Contractor is responsible shall not be taken into account;"]

Clause 2.26

In line 1, first paragraph, before ":" insert "(but only to the extent that such events are not in any way consequent upon or necessitated by any negligence, omission, default, breach of contract or breach of statutory duty of the Contractor, his servants or agents or any sub-contractor or supplier or their respective servants or agents)"

Clause 2.26.2.1

Delete clause 2.26.2.1 and insert "Not used."

Clause 2.26.2.2

In line 1 after "3.11" insert "(to the extent that the Employer's Requirements provided insufficient information to enable the Contractor to make a sufficient allowance prior to the issue of such instructions for the effects on programme of those instructions)"

Clause 2.26.2.3

Insert at the end of the clause "or unless the opening up for such inspection or test was reasonably required by reason of any similar, equivalent or associated work, materials or goods having been shown by a previous inspection or test not to be in accordance with this Contract"

Clause 2.26.5

After "clause 4.11" insert "or clause 8.10.3"

Clause 2.26.6

Add at the end of clause 2.26.6:

" or, in the case of any impediment or prevention save to the extent the same is in consequence of the reasonable exercise of the rights of the Employer under this Contract"

Clause 2.26.7

At the end of the clause insert "provided that the Contractor shall have supplied any information required, placed any necessary orders and otherwise performed his obligations under this Contract in respect of such work as soon as reasonably practical so as not to delay or disrupt the Statutory Undertaker in relation to such work"

Clause 2.26.8

Delete clause 2.26.8 and insert "weather conditions which the Met Office records in the area nearest the site demonstrate are exceptionally adverse for that time of year"

Clause 2.26.11

In line 3 after "materials required for them" insert "save where such events arise upon the site or concern the Contractor's employees and do not arise out of or in connection with a national labour dispute"

Clause 2.26.12

In line 3 before ";" insert "which the Contractor could not have reasonably foreseen at the Base Date"

Clause 2.26.13

Delete clause 2.26.13 and insert "Not used."

Clause 2.27A

Insert new clause 2.27A:

"2.27A.1	The Contractor shall give to the Employer four (4) weeks written notice of the anticipated date of practical completion of the Works or a Section and shall at the same time provide the Employer with:

2.27A.1.1	details of any works which remain to be completed within such four (4) week period;

2.27A.1.2	proposals and programming arrangements for the execution of such works before practical completion.

2.27A.2	The Employer's Agent shall, within such four (4) week period inspect the Works or Section with a view to issuing the Practical Completion Certificate or Section Completion Certificate in accordance with clause 2.27."

Clause 2.27

In line 1 delete "When" and insert "The Contractor shall notify the Employer in writing when he considers that the Works or a Section have reached practical completion.  Provided that"

Insert new paragraph at end of clause 2.27:

"The Employer at his discretion may issue the Practical Completion Statement or Section Completion Statement notwithstanding that minor items of work and/or final commissioning and adjustment of mechanical and electrical service installations remain to be completed, in which event the Contractor shall be obliged to complete such incomplete work and/or commissioning and adjustment within one month of the date of the Practical Completion Statement or Section Completion Statement or within such other period as the Employer may reasonably stipulate."

Clause 2.29.2

Delete clause 2.29.2 and insert:

"2.29.2 	A notice from the Employer under clause 2.29.1 shall state that for the period between the Completion Date and the date of practical completion of the Works (or the relevant Section) by the Contractor, or the date of termination of the Contractor's employment under this Contract (whichever is earlier):

2.29.2.1  	he requires the Contractor to pay liquidated damages at the rate stated in the Contract Particulars, or lesser rate stated in the notice, in which event the Employer may recover the same as a debt; and/or

2.29.2.2	that he will withhold or deduct liquidated damages at the rate stated in the Contract Particulars, or at such lesser stated rate, from sums due to the Contractor."

Clause 2.29.3

In line 3 before "." insert "provided that the fixing of such later Completion Date shall not invalidate the Employer's notice  as to deduction of liquidated and ascertained damages and the payment or repayment of the amounts under this clause shall be limited to the net difference between the amounts deducted and the amounts properly due after the fixing by the Employer of the later completion date.  Interest shall not be payable by the Employer on any amounts payable or repayable under this clause 2.29.3"

Clause 2.30

In lines 5-6 delete "The Contractor shall thereupon give to the Employer" and insert "The Employer shall thereupon give to the Contractor"

Clause 2.31

Insert at end of clause "provided however that the Rectification Period for the relevant part shall be deemed to be extended and shall run until the issue by the Employer of the Notice of Completion of Making Good in respect of the whole of the Works"

Clause 2.32

Insert at end of clause "provided that the Employer shall not be required to issue such notice any earlier than 14 days after the end of the Rectification Period applicable to such Relevant Part"

Clause 2.35

In line 1 of the final paragraph before "a reasonable time" insert " any time period specified in the Employer's Requirements commensurate with such defect, shrinkage or fault and, if not specified in the Employer's Requirements, within"

In lines 2 and 4 of the final paragraph insert "and any consequential damage to the Works" after "faults"

Insert at end of final paragraph of clause 2.35:

"provided that where the Employer states in his instruction that, in his opinion, any such defect, shrinkage or other fault is likely to cause unreasonable inconvenience to any person lawfully in occupation of or using the whole or any part of the Works or that such defect, shrinkage or other fault is likely directly or indirectly to cause any further damage to the Works the Contractor shall comply with the Employer's instruction forthwith and in any event within 48 hours from its receipt.

When entering upon the site to carry out any rectification or other works following the issue of any Practical Completion Statement or Section Completion Statement the Contractor shall cause as little disruption and inconvenience to any person lawfully in occupation of or using the whole or any part of the Works as reasonably possible and shall make good all damage caused by such entry and (other than in cases of emergency) comply with the reasonable security requirements of any such permitted occupier(s)."

Insert new paragraph at end of clause:

"The provisions of this clause 2.35 are without prejudice to any other rights and remedies the Employer may have."

Clause 2.36

Insert at end of clause "provided that the Employer shall not be required to issue any notice to that effect any earlier than 14 days after the end of the relevant Rectification Period"

Clause 2.37

Delete clause 2.37 and heading and insert:

"2.37.1	On or before practical completion of the Works or a Section the Contractor shall without further charge to the Employer supply for the retention and use of the Employer:

2.37.1.1	[two]complete copies of the as built drawings, plans, sections and specifications;

2.37.1.2	[one]draft of every maintenance and operating manual (including copies of all test and commissioning certificates and/or statements);

2.37.1.3	originals of all warranties, guarantees and certificates or other documents in respect of plant and machinery installed in the Works or Section;

2.37.1.4	a schedule listing the names and addresses of all sub-contractors, sub-consultants and suppliers who have been involved in or concerned with the Works or Section;

2.37.1.5	[one]copy of all maintenance and operating agreements;

2.37.1.6	the original notice of passing of plans under the Building Regulations and confirmation from the relevant authority that all conditions under the Building Regulations have been complied with; and

2.37.1.7	the original and [two]copies of the health and safety file.

[Notwithstanding any provision to the contrary in this Contract the Contractor shall not be entitled to any payment of Retention that would (but for this provision) become due and payable under this Contract until the provisions of clause this 2.37.1 have been complied with.]

2.37.2	Within three weeks of the date of the Practical Completion Statement or the relevant Section Completion Statement the Contractor shall without further charge to the Employer supply to the Employer (to the extent they have not been provided in accordance with clause 2.37.1):

2.37.2.1	[6 (six)]complete reproducible sets of the as built drawings;

2.37.2.2	[5 (five)]copies of all maintenance and operating manuals, test and commissioning certificates and statements and any service or other agreements available for all heating, air conditioning and other equipment, plant and machinery installed in the Works or Section;

2.37.2.3	all correspondence and documentation relating to obtaining of the Consents together with the originals of the Consents and copies of all associated drawings and plans and copies of all applications relative thereto;

2.37.2.4	evidence that all Consents have been obtained and complied with in full in relation to the Works or Section; and

2.37.2.5	the original completion certificate issued by the relevant authority under the Building Regulations.

2.37.3	If during the course of the Rectification Period errors are discovered in the drawings and information supplied by the Contractor in accordance with clauses 2.37.1 and 2.37.2 or if as the result of any adjustment or remedial work carried out during the course of the Rectification Period the said drawings and information no longer show or describe the Works as required by clause 2.37.1 or clause 2.37.2 then the Contractor as soon as reasonably practicable shall amend the said drawings and information so that they comply with the requirements of clause 2.37.1 or clause 2.37.2."

Clause 2.38.2

Delete clause 2.38.2 and insert:

"The Contractor hereby grants to the Employer an irrevocable royalty-free non-exclusive licence to use copy and reproduce the Contractor's Design Documents for any purpose whatsoever connected with the Works and/or the site including but without limitation the execution, completion, extension, maintenance, letting, management, sale, advertisement, alteration, reinstatement and repair of the Works and/or the site provided always that the Contractor shall not be liable for any such use by the Employer of the Contractor's Design Documents for any purpose other than that for which the same were prepared and provided by the Contractor."

Clause 2.38.3

Delete clause 2.38.3 and insert "The licence referred to in clause 2.38.2 carries the right to grant sub-licences and shall be transferable to third parties and shall subsist notwithstanding the determination (for any reason) of the Contractor's employment under this Contract."

Clause 2.38.4

Delete clause 2.38.4 and insert new clause 2.38.4:

"The Contractor waives absolutely all Moral Rights the Contractor may have in the Contractor's Design Documents and/or the Works and where it is not the author shall procure a waiver from the author of any Moral Rights the author may have in respect of the Contractor's Design Documents."

Clause 2.39

Insert new clause 2.39:

["On or before the Date of Possession (or if there are sections, on or before the first of the Dates of Possession) the Contractor shall provide to the Employer a programme for the carrying out of the Works and, if and whenever, there is any material delay to the execution of the Works the Contractor shall provide to the Employer a revised programme for the Works."]

or

["2.39.1	On or before the Date of Possession (or if there are Sections on or before the first of the Dates of Possession) the Contractor shall provide [2] copies of the programme for the execution of the Works to the Employer.  Such programme shall (at all times):

2.39.1.1	show the latest dates by which drawings, specifications and other details to be prepared by or on behalf of the Contractor are to be submitted to the Employer in accordance with Schedule 1;

2.39.1.2	meet the requirements of the Employer's Requirements;

2.39.1.3	show in reasonable detail the various activities comprised in the Works;

2.39.1.4	demonstrate the critical path network for the Works;

2.39.1.5	allow the Employer's Agent to clearly identify the interdependencies between the various activities comprised in the Works;

2.39.1.6	be produced in paper and electronic format or such format as the Employer's Agent reasonably requires.

2.39.2	Within 10 Business Days of it becoming apparent that the progress of the Works is being delayed or is likely to be delayed by any circumstances or that a change of programme is necessary to avoid or minimise delay and/or a decision of the Employer under clause 2.25 the Contractor shall supply [2] copies of a suitably amended or revised programme to the Employer."]

Clause 2.40

Insert new clause 2.40:

"The Employer has provided the Contractor with copies of the Third Party Agreements and the Contractor shall be deemed to have full knowledge of the requirements of the Third Party Agreements and shall perform the Works so as to ensure that the Employer and/or any Group Company are not put in breach of their obligations in the Third Party Agreements and/or rendered liable to pay compensation under any of the Third Party Agreements.["]

[The Employer may enter into further third party agreements with third parties relating to the Works after the date of this Contract.  Upon being supplied with copies of, or relevant extracts from, those agreements the Contractor shall, with effect from the date on which it was provided with copies or extracts, comply with the requirements of such further third party agreements to the extent they affect or relate to the carrying out of the Works and to the extent that they do not conflict with the terms of this Contract.  The Contractor's obligation to comply with such further third party agreements may amount to a Change."]

Insert new clause 2.41:

"The Contractor shall be deemed to have inspected and examined the site and its surroundings and to have satisfied himself before the date of this Contract or commencing the Works (whichever is the earlier) as to the nature of the ground, the sub-surface conditions and sub-soil, the form and nature of the site, the extent, nature and difficulty of the work and materials necessary for the completion of the Works, the means of communication with and restrictions of access to the site, the accommodation he may require, and in general to have obtained for himself all necessary information as to risks, contingencies and all other circumstances influencing or affecting the Works.  The Contractor shall not be entitled to any extension of time or to any additional payment on grounds of any misunderstanding or misinterpretation of any such matter, nor shall the Contractor be released from any of the risks accepted or obligations undertaken by him under this Contract on the ground that he did not or could not have foreseen any matter which might affect or have affected the execution of the Works."

Clause 2.42

Insert new clause 2.42:

"Without limitation to clause 2.41 in the inspection of the site the Contractor will be deemed to have determined the position of any obstructions and all underground and over-ground services and drainage and the Contract Sum shall be deemed to be inclusive of all costs which may be incurred in carrying out any diversions of the underground and over-ground services and/or drainage and the costs of the Contractor's operations in the vicinity of any such services (unless otherwise provided for in the Employer's Requirements).  Liaison with and obtaining the agreement of any public or statutory authority in this respect is the sole responsibility of the Contractor (unless otherwise provided for in the Employer's Requirements)."

Clause 2.43

Insert new clause 2.43:

"2.43.1	The Employer gives no warranty or representation as to:

2.43.1.1	the condition of the site or any adjoining property or any services in or under the site or

2.43.1.2	the accuracy or sufficiency of any surveys, tests or investigations and/or any soils or survey data contained in any document made available to the Contractor by the Employer or on the Employer's behalf or any recommendations or conclusions made or reached in any such document.

2.43.2	The Contractor shall ensure that all necessary tests, surveys and investigations are carried out and that the design takes their requirements into account."

Clause 2.44

Insert new clause 2.44:

"The Contractor shall not have or make any claim whether in contract or by way of negligent or innocent misrepresentation or otherwise, in respect of information provided or statements made by or on behalf of the Employer in respect of such risks contingencies or circumstances relating to the site provided that nothing in this clause shall operate to exclude or limit liability for fraud."

Clause 2.45

Insert new clause 2.45:

"Without prejudice to the generality of clause 6.2 the Contractor shall at all times take all reasonable steps to prevent any nuisance (including, but without limitation, any noisy working operations, noxious fumes or the deposit on public highways of any material or debris) or other interference with the rights of any adjoining landowner, tenant or occupier or any statutory undertaker arising out of the carrying out of the Works or of any obligation pursuant to clauses 2.35 to 2.36 and shall defend or, at the Employer's option, assist the Employer in defending any action or proceeding which may be instituted in relation thereto.  The Contractor shall be liable for and shall indemnify the Employer from and against any and all expenses, liabilities, losses, claims and proceedings resulting from any failure or default by the Contractor in performing his obligations under this clause 2.45 save only where such nuisance or interference is the consequence of a Change or other instruction of the Employer (which is not itself the result of any negligence, default or breach of contract by or on behalf of the Contractor) and which could not have been avoided by the Contractor using all reasonable and practical means."

Clause 2.46

Insert new clause 2.46:

"Without prejudice to the Contractor's obligations under clause 2.45 if the carrying out of the Works or of any obligation pursuant to clauses 2.35 to 2.36 is likely to necessitate any interference with the rights of adjoining or neighbouring landowners tenants or occupiers then the Contractor shall without cost to the Employer obtain the prior written agreement of such landowner, tenants and/or occupiers and such agreement shall be subject to the approval of the Employer before execution.  The Contractor shall comply in every respect with any conditions contained in such agreement."

Clause 2.47

Insert new clause 2.47:

"Without prejudice to the obligations of the Contractor under clauses 2.45 and 2.46 the Contractor shall at all times ensure that there is no trespass by the Contractor, its servants, agents, sub-contractors, consultants or suppliers (including without limitation the over sailing of tower crane jibs) on or over any adjoining or neighbouring property arising out of, or in the course of, or caused by the carrying out of the Works and shall take all reasonable safety and other measures to prevent damage or injury to any persons (including but without limitation) the occupiers of adjoining or neighbouring property and members of the public."

Clause 2.48

Insert new clause 2.48:

"2.48.1	The Parties will each act in the capacity of Data Controller in respect of the Personal Data Processed under this Agreement and each will Process the Personal Data as independent Data Controllers.

2.48.2	The Parties (including their employees, agents or officers) shall at all times during the period of this Agreement comply with the provisions and obligations imposed by this clause 2.48 and the Data Protection Legislation generally, including any requirement to obtain registrations, consents, and provide notifications and relevant privacy information to Data Subjects as required for the purposes of their obligations under this Agreement.

2.48.3	The Parties warrant and represent that they each have in place appropriate technical and organisational measures to protect the Personal Data against accidental or unlawful destruction or accidental loss, alteration, unauthorised disclosure or access, and which provide a level of security appropriate to the risk represented by the processing and the nature of the data to be protected.

2.48.4	Each Party shall notify the other without undue delay on becoming aware of any breach of the Data Protection Legislation in relation to the Personal Data Processed under this Agreement.

2.48.5	Whilst each Party shall be responsible for responding to any complaint in relation to the Personal Data Processed pursuant to this Agreement, or any request by individuals to exercise the Data Subject's Rights, the Parties will co-operate with each other and provide reasonable assistance with any request, proceedings or inquiry by any affected Data Subject and/or the Information Commissioner or other body authorised by statute which are concerned with the Data Protection Legislation in connection with data processed under this Agreement.

2.48.6	The provision of this clause 2.48 shall apply during the continuance of the Agreement and indefinitely after its termination."

Section 3 - Control of the Works

Clause 3.1

In line 1 after "Employer" insert "(including for the avoidance of doubt the Purchaser's Surveyor and/or Tenant's Surveyor and/or Funder's Surveyor)"

In lines 4-5 delete "so far as possible"

At end of clause insert:

"The Contractor shall provide facilities and necessary equipment for inspection of the Works by the Employer's Agent and any person authorised by him or the Employer (including for the avoidance of doubt the Purchaser's Surveyor and/or Tenant's Surveyor and/or Funder's Surveyor)"

Clause 3.2

Delete clause 3.2 and insert:

“3.2.1	The Contractor shall at all times keep upon the Works and deploy full time in relation to the Works the person in charge named in the Contractor’s Proposals, who shall be appropriately competent and experienced to undertake this role. Such person shall act as the Contractor’s representative in charge of the Works and any instructions given to the Contractor's representative by the Employer’s Agent shall be deemed to have been issued to the Contractor.

3.2.2	The Contractor shall procure that the services of any key person named in the Contractor’s Proposals shall be available during the carrying out of the Works and that each key person shall devote such time and attention as may be necessary to ensure the proper carrying out by the Contractor of the Works.

3.2.3	The Contractor shall not remove the person-in-charge referred to in clause 3.2.1 or any key person referred to in clause 3.2.2, nor select their replacement, without the prior approval of the Employer (such approval not to be unreasonably withheld or delayed).

3.2.4	The Employer may request the removal of the person-in-charge referred to in clause 3.2.1, any key person referred to in clause 3.2.2 or other persons engaged on the Works if in the Employer’s opinion (not to be exercised unreasonably or vexatiously) his performance or conduct is or has been unsatisfactory. The Contractor shall promptly remove such person and replace him with such other person as the Employer shall have first approved (such approval not to be unreasonably withheld or delayed).

3.2.5	Any costs incurred by the Contractor in replacing any person in accordance with this clause 3.2 (in any circumstances) shall be borne by the Contractor."

Clause 3.4.1

At the beginning of line 1 insert "subject to clause 8.7.2.3"

Clause 3.4.2.5

Delete clause 3.4.2.5 and insert:

"that if the sub-contractor is a Sub-Contractor they shall execute and deliver within 10 Business Days of a written request as deeds a collateral warranty or collateral warranties in the respective forms contained in Appendix 6 to the Agreement in favour of the Employer and/or Purchaser and/or Tenants and/or Funder coupled with a provision to the effect that the Contractor shall not be obliged to make any payment or further payment to the Sub-Contractor concerned in circumstances where such a collateral warranty has been requested but not executed and delivered within the ten (10) Business Day period;"

Clause 3.4.2.6

Insert new clause 3.4.2.6:

"that if the sub-contractor is a Sub-Contractor and is carrying out any design or other professional services that the sub-contractor maintains professional indemnity insurance cover at a level reasonably acceptable to the Employer with a reputable insurer for a period of 12 (twelve) years from practical completion and that it shall provide sufficient evidence of such insurance;"

Clause 3.4.2.7

Insert new clause 3.4.2.7:

"for provisions which comply with the requirements of clause 8.6.4;"

Clause 3.5.1

Delete clause 3.5.1 and insert "Not used".

Clause 3.6

In line 5 delete "and an appropriate deduction shall be made from the Contract Sum" and insert "which amount may be deducted by him from any sums due or to become due to the Contractor under this Contract or may be recoverable from the Contractor by the Employer as a debt"

Clause 3.8

Delete second sentence and insert "Notwithstanding such request the Contractor shall comply with the said instruction and unless it is subsequently decided in any adjudication or legal proceedings that the provision specified by the Employer in answer to the Contractor's request does not empower the issue of the said instruction, then the issue of the same shall be deemed for all the purposes of this Contract to have been empowered by the provision of the Conditions specified by the Employer."

Clause 3.9.1

Delete clause 3.9.1 and insert "Subject to clause 3.9.4 the Employer may issue instructions effecting a change in the Employer's Requirements."

Clause 3.9.2

Delete clause 3.9.2 and insert "Not used."

Clause 3.11

In line 1 delete "The" and insert "If and as required, the"

Clause 3.12In line 1 after "to" insert "provide samples of materials or"

At the end of the clause insert "or unless the opening up for such inspection or test was reasonably required by reason of any similar, equivalent or associated work, materials or goods having been shown by a previous inspection or test not to be in accordance with this Contract"

Clause 3.13.1

In line 1 after "removal from the site" insert "or rectification"

Clause 3.13.3

At the end of the clause insert "or unless the opening up for such inspection or test was reasonably required by reason of any similar, equivalent or associated work, materials or goods having been shown by a previous inspection or test not to be in accordance with this Contract"

Clause 3.16

Delete clause 3.16 and insert:

"Each Party undertakes to the other that in relation to the Works and site he will duly comply with applicable CDM Regulations. In particular but without limitation:

- 3.16.1 	where the Contractor is not the Principal Designer, the Employer shall ensure that the Principal Designer carries out his duties and, where the Contractor is not the Principal Contractor, shall ensure that the Principal Contractor carries out his duties under those regulations;

3.16.2	where the Contractor is and while he remains the Principal Designer, he shall comply with the duties of a Principal Designer and shall without charge prepare, and deliver to the Employer, the health and safety file and the Contractor hereby agrees to indemnify and indemnifies the Employer against all costs, expenses, proceedings and/or claims howsoever arising as a result of non- compliance by the Contractor of his obligations under this clause;

3.16.3	the Contractor shall comply with regulations 8 to 10 and 15 and, where he is the Principal Contractor, with regulations 12 to 14 and the Contractor hereby agrees to indemnify and indemnifies the Employer against all costs, expenses, proceedings and/or claims howsoever arising as a result of non-compliance by the Contractor of his obligations under this clause;

3.16.4	whether or not the Contractor is the Principal Contractor, compliance by the Contractor with his duties under the regulations, including any such directions as are referred to in regulation 15(3), shall be at no cost to the Employer and shall not entitle the Contractor to an extension of time;

3.16.5	if the Employer appoints a replacement for the Principal Designer or Principal Contractor, the Employer shall immediately upon that appointment notify the Contractor with details of the new appointee."

Clause 3.17

Insert new clause 3.17:

"The Contractor shall (to the extent that it has not already done so) forthwith sign as deeds and complete Deeds of Novation with the Novated Consultants."

Clause 3.18

Insert new clause 3.18:

"The Contractor shall obtain the Employer's approval to the form of the appointment of any Sub-Consultant (in addition to the approval required by clause 3.3.2) which appointment (without limitation) shall:

3.18.1	be executed as a deed;

3.18.2	include an obligation on the Sub-Consultant to execute and deliver as a deed within 10 Business Days of a request to do so a deed or deeds of collateral warranty in favour of the Employer and/or Purchaser and/or Tenant and/or Funder in the form set out at Appendix 7 to the Agreement;

3.18.3	include a provision to the effect that the Contractor shall not be obliged to make any payment or further payment to the Sub-Consultant concerned in circumstances where such a collateral warranty has been requested but not executed and delivered within the 10 Business Day period referred to in clause 3.18.2;

3.18.4	to the extent that any Sub-Consultant is carrying out any design or other professional services include an obligation to maintain professional indemnity insurance cover at a level reasonably acceptable to the Employer for a period of twelve years from practical completion with a reputable insurer and to provide sufficient evidence of such insurance;

3.18.5	include provisions which comply with the requirements of clause 8.6.4."

Clause 3.19

Insert new clause 3.19:

"In relation to the appointments of [the Novated Consultants and] any Sub-Consultants the Contractor shall:

3.19.1	properly enforce the obligations of such consultants under their appointments and shall not determine or vary the terms of any such appointments or release such consultants from their obligations under their respective appointments without the prior consent of the Employer;

3.19.2	(without limitation to clause 3.19.1) procure that such consultants comply with their obligations in relation to the provision of collateral warranties under the terms of their appointments;

3.19.3	duly perform and observe all the obligations and duties on the part of the Contractor under the appointments;

3.19.4	ensure that the [Novated Consultants and] Sub-Consultants are fully and properly instructed in connection with the Works;

3.19.5	diligently take all steps necessary effectually to procure due performance and observance of the obligations and duties of [the Novated Consultants and] the Sub-Consultants;

3.19.6	not waive, release, vary or estop itself from enforcing or seeking redress for any such obligation or duty without the consent of the Employer;

3.19.7	not do or omit to do any act or thing which would entitle any of [the Novated Consultants and/or] the Sub-Consultants to treat as terminated by breach their appointment in connection with the Works."

Clause 3.20

Insert new clause 3.20:

"The Contractor acknowledges that the Contractor's liability under this Contract shall not be released, diminished or in any other way affected by:

3.20.1	any direction, admission, approach, consent, approval, confirmation, comment, sanction, acknowledgement or advice made or given by or on behalf of the Employer or the Employer's Agent;

3.20.2	any act, omission or delay by or on behalf of the Employer in inspecting approving or informing itself about anything relating to the Works;

3.20.3	any enquiry or inspection into any relevant matter which may be made or carried out by or on behalf of the Employer or the Employer's Agent;

3.20.4	the inclusion of the value of any work, materials or goods in any Interim Payment;

3.20.5	the appointment or failure to appoint any clerk of works or other person to inspect or otherwise report in respect of the Works or by any act or omission of any clerk of works or other person whether or not such act or omission might give rise to an independent liability of such clerk of works or another person to the Employer, the Employer's Agent and/or any third party;

3.20.6	the issue of the Practical Completion Statement, any Section Completion Statement and/or the Notice of Completion of Making Good."

Clause 3.21

Insert new clause 3.21:

"Should the Employer issue an instruction pursuant to this Contract which could in any way be deemed, but for the provisions of clause 3.20, to relieve the Contractor from his liabilities or obligations or be against statute or good building practice, then the Contractor shall notify the Employer in writing of the effect of such instruction and the Employer shall then confirm whether or not the instruction remains effective within 5 Business Days."

Section 4 – Payment

Delete clause 4.4 and insert:

"4.4.1	The Parties agree and confirm that the procedure for the payment of VAT (if any) by 	either Party to the other shall be governed entirely and exclusively by the provisions of 	this clause 4 notwithstanding any other provision of this Agreement.

4.4.2 	Subject to clause 4.4.8, any consideration (whether monetary consideration or non-	monetary consideration) paid or provided under or in connection with this Agreement is 	to be treated as exclusive of any VAT.  If the person making the supply (or the 	representative member of the VAT group of which it is a member) is required to 	account for VAT on any supply, the recipient of the supply shall pay (in addition to 	paying or providing any other consideration) an amount equal to the amount of that VAT 	upon the later of:

4.4.2.1	the time for payment or provision of the consideration; and

4.4.2.2	the receipt by the recipient of the supply of a VAT invoice in respect of that 	VAT.

4.4.3	The Parties acknowledge that the Employer has not confirmed in writing whether the 	requirements specified in article 8(1)(b) of the Order are satisfied in respect of any 	Supply.

4.4.4	The Parties consider that the Reverse Charge will apply to the Supplies so that it is for 	the Employer, on the Contractor's behalf, to account for and pay VAT on the Supplies 	and not for the Contractor.

4.4.5	During such time as the Reverse Charge applies to the Supplies and no later than 5 	(five) Business Days before any payment by the Employer for the Supplies, the 	Contractor will provide to the Employer an invoice (which is not a VAT invoice and which 	will not include any demand for any amount in respect of VAT) showing all the 	information 	normally required to be shown on a VAT invoice in respect of the payment 	in question, 	including without prejudice to the generality of the foregoing, the amount of 	VAT due on the payment (subject to the Reverse Charge) and a breakdown of values by 	VAT rate. The Contractor will also annotate such invoice as follows: "Reverse charge: 	VAT Act 1994 Section 55A applies".

4.4.6	The Contractor shall promptly provide any information reasonably requested by the 	Employer to assist the Employer in complying with its obligations under the Reverse 	Charge or in providing any information requested of the Employer by HMRC.

4.4.7	If the requirements in article (8)(2)(a) and (b) of the Order are met in relation to any 	Supply, the 	Employer and the Contractor, pursuant to article 8(2)(c) of the Order, agree 	to treat the 	Supplies as not being excepted supplies (within the meaning of articles 3(2) 	and 8 of the Order).

4.4.8	Notwithstanding clause 4.4.2, where the Employer has operated the Reverse Charge on 	Supplies but HMRC confirms in writing to the Employer that the Reverse Charge does 	not apply in respect of those Supplies and that, notwithstanding that the Employer has 	operated the Reverse Charge, the Contractor has to account for VAT in respect of those 	Supplies then, subject to receipt by the Employer of a valid VAT invoice from the 	Contractor, 	the Employer will pay the VAT due on those Supplies to the Contractor 	within 5 (five) Business Days after the later of:

4.4.8.1	obtaining any net repayment or credit from HMRC arising from the incorrect operation of the Reverse Charge after correcting both:

(a)	the output tax overpaid to HMRC by the Employer (for which the Employer would obtain a repayment or credit); and

(b)	the input tax overpaid to the Employer by HMRC (which the Employer would owe to HMRC); and

4.4.8.2	obtaining repayment or credit from HMRC in respect of the VAT due on the relevant Supplies to the Contractor,

and the Employer undertakes to claim such repayment or credit from HMRC without unreasonable delay after receiving confirmation from HMRC or a valid VAT invoice from the Contractor, each as mentioned above."]

Clause 4.9.1

In line 1 delete "14 days" and insert "28 days"

Clause 4.9.6

At the end of the clause insert "The Contractor confirms that the interest paid pursuant to this clause is a substantial remedy for late payment in compliance with section 9 The Late Payment of Commercial Debts (Interest) Act 1998."

Clause 4.9.8

Insert new clause 4.9.8:

"Where a notice complying with clause 4.9.5 has been given and either Party refers a dispute concerning such notice(s) to adjudication under clause 9.2 and the Adjudicator finds that any further amount over and above that set out in the notice should be paid then payment of such amount should be made not later than 7 days from the date of the Adjudicator's decision or the final date for that instalment whichever is the later."

Clause 4.10.4

In line 1 delete "The Employer's fiduciary interest in the Retention as stated in clause 4.16 shall not prevent him exercising" and insert "The Employer may exercise"

Clause 4.13.1.2

In line 2 before "and they are not on the Works prematurely" insert ", the Contractor has complied with clause 2.21"

Clause 4.15.2.1

After ";" delete "and"

Clause 4.15.2.2

After ";" insert "and"

Clause 4.15.2.3

Insert new clause 4.15.2.3 "nothing remains to be done to such Listed Items to complete the same up to the point of their inclusion in the Works;"

Clause 4.16

Delete clause 4.16 and insert:

"The Employer's interest in the Retention shall not be fiduciary and the relationship of the Employer and the Contractor with regard to the same shall be solely that of debtor and unsecured creditor.  Any right of the Employer to deduct or to set off any amount (whether arising under any express term or under any rule of law or equity) shall be exercisable against any monies due or to become due to the Contractor whether or not such monies consist of or include any Retention.  The Employer shall:

4.16.1	have no obligation to invest the Retention or any part of the Retention;

4.16.2	have no obligation to segregate the Retention or any part of the Retention in a separate bank account or in any other manner;

4.16.3	be entitled to the full and unencumbered beneficial interest in the Retention or any part of the Retention (including without limitation interest and income arising from the Retention)."

Clause 4.17.3

In line 3 after "issued after the date of failure" insert "provided that the Retention Percentage shall be calculated in relation to the amount of all the Interim Payments made rather than the total amount included in any Interim Payment"

Clause 4.18.2

At the end of clause 4.18.2 insert new paragraph:

"provided always where the Employer has exercised its discretion under clause 2.27 and notwithstanding any other provisions of this Contract, the Employer shall not be obliged to pay to the Contractor any part of the Retention deducted prior to and upon practical completion, unless and until the Contractor has carried out and completed to the reasonable satisfaction of the Employer, all work and/or remedied all defects in the Works as may be notified to the Contractor as outstanding and to be carried out or remedied (as the case may be) as a condition of practical completion, or as may be detailed in any list annexed to Practical Completion Statement or any Section Completion Statement, provided that if the Employer has been unable for any reason to provide access to the Contractor to remedy or complete defects or outstanding work within three months of the date of practical completion, the Employer shall pay to the Contractor the half of Retention otherwise due when the work has reached practical completion."

Clause 4.18.2.1

In line 2 before ";" insert "or where the drawings and other information referred to in clause 2.37 have not been provided to the Employer"

Clause 4.18.2.2

At the end of the clause insert "or for which the drawings and other information referred to in clause 2.37 have not been provided to the Employer"

Clause 4.19.1

In line 4, after "Relevant Matter" add "and the Contractor has made reasonable and proper efforts to avoid or reduce such loss and expense".

In line 4, after " subject to clause 4.19.2" add " and clause 4.19.3".

Clause 4.19.3

Insert new clause 4.19.3:

"No such entitlement arises to the extent the loss and/or expense includes any element of loss and/or expense which was contributed to by a cause other than a Relevant Matter."

Clause 4.19.4

Insert new clause 4.19.4:

"Notwithstanding any other provision of this clause 4.19 and clause 4.21, the Contractor shall not become entitled to the addition of any amount to the Contract Sum or to any other payment (other than any amount which is recovered by the Employer under any policy of insurance maintained in accordance with this Contract) in respect of any costs, loss or expense incurred by reason of any error, omission, negligence or default of the Contractor, his employees or agents or of any sub-contractor or supplier or any of their employees or agents."

Clause 4.21.2.2

In line 2 after "or test" insert "or series of inspections or tests"

At the end of clause before ";" insert "or unless the inspection or test was reasonably required as a result of a previous inspection or test or series thereof"

Clause 4.21.4

Delete clause 4.21.4 and insert "Not used."

Clause 4.21.5

Add at the end of clause 4.21.5:

"or, in the case of any impediment or prevention save to the extent that the same is in consequence

of the reasonable exercise of the rights of the Employer under this Contract."

Clause 4.23

Delete clause 4.23 and insert:

"Reimbursement of the Contractor for loss and/or expense under clauses 4.19 to 4.22 shall be deemed to be full compensation for the Contractor in respect of which the compensation is paid and the Employer shall have no further liability to the Contractor in respect of such matters arising under the Contractor or generally at law."

Clause 4.24.2

In line 4 of the final paragraph before "." insert "and to what they relate".

Clause 4.24.4

In line 2 after "the 2 month notice period" insert "and at least 1 month before the due date for the final payment"

Clause 4.24.5.3

Delete clause 4.24.5.3 and insert "Not used."

Clause 4.24.7

Insert new clause 4.24.7:

"Where a notice complying with clause 4.8 has been given and either Party refers a dispute concerning such notice(s) to adjudication under clause 9.2 and the Adjudicator finds that any further amount over and above that set out in the notice should be paid then payment of such amount should be made not later than 7 days from the date of the Adjudicator's decision or the final date for payment whichever is the later."

Section 5 - Changes

Clause 5.1.2.3

After ";" delete "or"

Clause 5.1.2.4

After "execution" insert ", sequencing"

Delete "." at the end of the clause and insert "; or"

Clause 5.1.2.5

Insert new clause 5.1.2.5:

"the acceleration, deceleration and/or suspension of the Works or any part or parts of the Works;"

Clause 5.1.2

At end of clause 5.1.2 insert:

"provided that such imposition, addition, alteration or omission shall not be treated as a Change requiring an adjustment to the Contract Sum or an extension of time insofar as it is instructed as a result of or in consequence of any negligence, default or breach on the part of the Contractor or any of the Contractor's Persons"

Clause 5.8

Insert new clause 5.8:

"Valuations of additional or substituted work shall not change the amount included in the Contract Sum under the heading Preliminaries unless it can be shown that the change directly affects the assumptions made or which ought reasonably to have been made by the Contractor in preparing his tender."

Clause 5.9

Insert new clause 5.9:

"The allowance for profit and overheads within the Contract Sum Analysis shall be adjusted pro rata to the value of any additional or substituted work."

Clause 5.10

Insert new clause 5.10:

"In the event that any part or parts of the Works are omitted by virtue of any instruction pursuant to this clause 5, whether relating to a Provisional Sum item or otherwise, the Employer shall not be liable to the Contractor for any loss of profit, overheads, supervision, insurances and/or other preliminary items and/or contracts and/or any other costs, losses and/or expenses arising out of or in connection with the omission of such works"

Section 6 – Injury, damage and insurance

Clause 6.1

In line 3 after "carrying out of the Works" insert "including the performance of the Contractor's obligations under clause 2.35 or out of the presence on site of any Contractor's Person for any other reason"

Clause 6.2

In line 3 after "or personal" insert "(including any expense, liability, loss or claim arising from but not limited to obstruction, trespass, nuisance or interference with any rights of way, light, air or water)"

In line 4 after "the Works" insert "or of any obligation pursuant to clause 2.35"

Clause 6.4.1

In line 2 after "effect" insert "(with reputable insurers based in the UK approved by the Employer (such approval not to be unreasonably withheld or delayed))"

In line 2 after "maintain" insert "until the issue of the Notice of Completion of Making Good"

Clause 6.4.3

Insert new clause 6.4.3:

"The Contractor shall not do or permit or suffer to be done upon the site or any part of the site any act or thing which may vitiate any policy or policies of insurance effected by the Contractor or (insofar as they have been notified to the Contractor) any policy or policies of insurance effected by the Employer and/or Funder and/or Purchaser and/or any Tenant."

Clause 6.4.4

Insert new clause 6.4.4:

"The Contractor shall not permit any variation of insurance cover effected pursuant to clause 6.4.1 without the prior written approval of the Employer and shall immediately notify the Employer of any endorsements or other amendments to the relevant policies received from the insurers."

Clause 6.7

Insert at end of clause "Option A, B or C whichever is applicable shall not affect the responsibility of the Contractor or the Employer under this Contract for any loss or damage not covered by any Joint Names Policy."

Clause 6.8

In line 1 of the definition of All Risks Insurance after "damage to" insert "(subject to such excess and other customary exclusions and limitations as shall be approved by the Employer)"

In line 1 of the definition of Joint Names Policy after "the Contractor" insert "and any Funders/Purchasers and Tenants"

Clause 6.11.3

Delete from and including "," in line 2 to the end of the clause and insert:

":

6.11.3.1	(where the Contractor has notified a reduction in the scope or level of cover pursuant to clause 6.11.1) the Contractor shall continue to maintain Terrorism Cover at such reduced level or scope of cover;

6.11.3.2	the Employer may instruct the Contractor to effect and maintain any alternative or additional form of Terrorism Cover then reasonably obtainable by the Contractor, the net additional cost to the Contractor of any such cover and its renewal shall be added to the amounts payable to the Contractor."

Clause 6.15

Delete clause 6.15 and insert:

"6.15.1	The Contractor shall effect and maintain professional indemnity insurance in the sum and on the basis set out in the Contract Particulars without unusual or onerous conditions or excesses with reputable insurers carrying on business in the UK with effect from the date of commencement of the Works and for a period expiring no earlier than 12 years from practical completion provided that such insurance remains available to organisations of equivalent size and type to the Contractor's business at commercially reasonable rates and on commercially reasonable terms.

6.15.2	The Contractor undertakes to provide to the Employer on demand from time to time such evidence as the Employer may reasonably require to satisfy himself that the insurance required by clause 6.15.1 is being maintained.

6.15.3	The Contractor shall inform the Employer if the insurance required by clause 6.15.1 is not maintained or renewed or for any reason becomes void or unenforceable or ceases to be available at commercially reasonable rates and terms and shall agree with the Employer the best means of protecting the Contractor's and the Employer's respective interests and carry out such actions as shall be necessary to implement any agreed actions.

6.15.4	The Contractor shall not compromise settle or waive any insurance claim it may have relating to any liability under this Contract without the Employer's prior consent provided that nothing in this clause shall prevent the Contractor's insurers from taking over (in the Contractor's name) the defence of any claim made by the Employer under this Contract (in that capacity) from conducting and settling it as they see fit.

6.15.5	The above obligations shall continue notwithstanding termination of this Contract or determination of the Contractor's employment under this Contract in either case for any reason whatsoever."

Clause 6.16

Delete clause 6.16 and insert "Not used."

Section 7 – Assignment, third party rights and collateral warranties

Clause 7.1

Delete clause 7.1 and insert:

"7.1.1	The Employer may assign its entire rights and benefits under this Contract to any person having or acquiring an interest in the Works and the Employer's said rights and benefits may be charged and/or assigned by way of security and may be re-assigned on redemption.  The Contractor may not assign the benefit of this Contract without the written consent of the Employer.

7.1.2	The Contractor undertakes with the Employer not to contend that any person to whom this Contract may be assigned will be precluded from recovering under this Contract any loss resulting from any breach of this Contract either by reason that the person is an assignee and not the original party to this Contract or by reason that the Employer named in this Contract or any intermediate owner of the Employer's interest in the Works shall escape loss resulting from such breach by reason of the disposal of its interest in the Works."

Clause 7.2

Delete clause 7.2 and insert "Not used."

Clause 7.3

At the end of the clause insert:

"Notwithstanding any other terms of this Contract, if the Contractor does not provide to the Employer the performance bond or guarantee referred to in clause 7.3.1 above, the Employer shall be entitled to withhold  ten per cent (10%) of the value of each and every following Interim Payment or Final Statement or Employer's Final Statement as the case may be until the said performance bond or guarantee is so provided. If the Contractor's parent company does not provide to the Employer the guarantee referred to in clause 7.3.2 above, the Employer shall be entitled to withhold one hundred per cent (100%) of the value of each and every following Interim Payment or Final Statement or Employer's Final Statement as the case may be until the said guarantee is so provided. Any amounts so retained shall become due to the Contractor on the due date of the Interim Payment or the final payment following the provision of the relevant bond or guarantee duly executed to the Employer."

Clause 7.4.2

Delete clause 7.4.2.

Clause 7.4.3

Delete clause 7.4.3.

Clause 7.5

Delete clause 7.5 and insert "Not used."

Clause 7.6

In line 1 delete "Where this Contract is executed as a deed, any" and insert "Any".  Delete second sentence.

Clause 7A.1

Delete clause 7A.1 and insert "P&T Rights shall vest in a Purchaser or Tenant on the date of receipt by the Contractor of a completed Nominating Notice to that effect stating the name of the Purchaser or Tenant and the nature of his interest in the Works"

Clause 7A.2

Delete "Part 1 of Schedule 5 (Third Party Rights for Purchasers and Tenants)" and insert "the P&T Rights"

Clause 7B.1

Delete clause 7B.1 and insert "Funder Rights shall vest in a Funder on the date of receipt by the Contractor of a completed Nominating Notice to that effect stating the name of the Funder, the nature of his interest in the Works and, if applicable, priority of step-in rights."

Clause 7B.2.1

Delete "Part 2 of Schedule 5 (Third Party Rights for a Funder)" and insert "the Funder Rights"

Clause 7B.2.2

Delete "paragraph 6 of Part 2 of Schedule 5 and insert "paragraph 4 of the Funder Rights"

Clause 7B.2

In the final paragraph delete "paragraph 5 or paragraph 6.4 of Part 2 of Schedule 5" and insert "paragraph 4 of the Funder Rights"

Clause 7C

Delete clause 7C and existing heading and insert:

"7C.1	Unless a Nominating Notice in favour of the relevant party has been served pursuant to clause 7A or clause 7B (as applicable) the Contractor shall execute and deliver to the Employer within 10 Business Days of a written request to do so from or on behalf of the Employer from time to time collateral warranties in favour of any:

      - Purchaser; and/or

      - Tenant; and/or

      - Funder.

Such collateral warranty or warranties shall be in the appropriate form set out in Appendix 5 to the Agreement with only such changes as the Employer may approve.

7C.2	Notwithstanding any other terms of this Contract, if the Contractor does not provide to the Employer the collateral warranties requested pursuant to this clause 7C, the Employer shall be entitled to withhold one hundred per cent (100%) of the value of each and every following Interim Payment or Final Statement or Employer's Final Statement as the case may be until all collateral warranties requested are so provided. Any amounts so retained shall become due to the Contractor on the due date of the Interim Payment or the final payment following the provision of the warranties duly executed to the Employer."

Clause 7D

Delete clause 7D and insert "Not used."

Clause 7E

Delete clause 7E and heading and insert:

"7E.1	The Contractor shall procure that each and every Sub-Contractor[,] [and] Sub-Consultant [and Novated Consultant] shall execute and deliver to the Employer within 15 Business Days of a request to do so from or on behalf of the Employer from time to time a collateral warranty or warranties in favour of:

      - the Employer; and/or

      - any Purchaser; and/or

      - any Tenant; and/or

      - any Funder.

Such collateral warranty or warranties to be in the appropriate form set out in Appendix 6 and/ or Appendix 7 to the Agreement with only such changes as the Employer may approve (such approval not to be unreasonably withheld or delayed).

7E.2	If the Contractor fails to procure the execution and delivery to the Employer of such deed or deeds of warranty within 15 Business Days of the request to do so the Employer shall be entitled to withhold:

7E.2.1	any and all sums relating to the work of the relevant Sub-Contractor(s) then in default and which would otherwise be due and payable under the terms of this Contract in each and every following Interim Payment or Final Statement or Employer's Final Statement as the case may be; and/or

7E.2.2	any and all sums relating to the services of the relevant [Novated Consultant and/or] Sub-Consultant then in default and which would otherwise be due and payable under the terms of this Contract in each and every following Interim Payment or Final Statement or Employer's Final Statement as the case may be.

Any amounts so retained shall become due to the Contractor on the due date of the Interim Payment or the final payment following the provision of the warranties from the relevant Sub-Contractor[, Novated Consultant] or Sub-Consultant duly executed to the Employer.

7E.3	The Contractor shall provide to the Employer within 5 Business Days of completion of the same a certified copy of:

7E.3.1	the completed appointment between the Contractor and each Sub-Consultant; and

7E.3.2	each sub-contract between the Contractor and every Sub-Contractor provided that the Contractor shall be entitled to delete the sub-contract sum and any commercially sensitive information from the certified copy of the sub-contract documentation to be provided in accordance with this clause."

Clause 7F

Insert new clause 7F:

"The Contractor shall obtain all warranties and guarantees available from manufacturers and suppliers of all goods and equipment forming part of the Works whether or not expressly indicated in the Employer's Requirements and shall ensure that the same are issued in favour of the Employer and handed over to the Employer as a condition precedent to practical completion of the Works."

Section 8 - Termination

Clause 8.1.4.1

Delete "he enters into an arrangement, compromise or composition in satisfaction of his debts" and insert:

"he commences negotiations with all or any class of his creditors with a view to rescheduling any of his debts, or makes a proposal for or enters into any compromise or arrangements with any of his creditors"

Clause 8.1.4.2

Delete the full stop and insert "; or"

Clause 8.1.4.3

Insert a new clause 8.1.4.3:

"he applies to court for, or obtains, a moratorium under Part A1 of the Insolvency Act 1986."

Clause 8.4.1.4

Delete "7.1" and insert "7.1.1"

Clause 8.4.1.6

Insert new clause 8.4.1.6:

"fails to provide a performance bond and/or a parent company guarantee"

Clause 8.5.4

Insert new clause 8.5.4:

"Ownership in all existing Contractor's Design Documents and other physical embodiments of designs relating to the Works shall transfer from the Contractor to the Employer immediately prior to the Contractor becoming Insolvent."

Clause 8.6

Delete clause 8.6 and insert:

- 8.6	"The Contractor undertakes to the Employer that:

- 8.6.1	it has not and its current and former directors, officers and employees have not and shall not engage in any Corrupt Activity;

- 8.6.2	it has not and its current and former directors, officers and employees have not and shall not engage in any activity, practice or conduct which could or would place the Employer in breach of section 7(1) Bribery Act or sections 45(1) or 46(1) Criminal Finances Act;

- 8.6.3	[it has and shall maintain and implement:

- 8.6.3.1	procedures to ensure compliance with clauses 8.6.1 and 8.6.2; and

- 8.6.3.2	(in the case of section 7 Bribery Act) adequate procedures and (in the case of sections 45 and 46 Criminal Finances Act) reasonable procedures designed to prevent any Associated Person from undertaking any Corrupt Activity and/or conduct that would give rise to an offence under section 7 Bribery Act or sections 45(1) or 46(1) Criminal Finances Act;]

- or

- [it shall comply with the Employer's Anti-corruption Policy;]

- 8.6.4	it shall include undertakings similar to those contained in this clause 8.6 in any contract it may enter into with sub-consultants, sub-contractors and suppliers and provisions similar to those contained in clause 8.6.6 [which shall be capable of enforcement directly by the Employer pursuant to the Contracts (Rights of Third Parties) Act 1999];]

- 8.6.5	from time to time, at the reasonable request of the Employer, it will confirm in writing that it has complied with its undertakings under clauses 8.6.1 to 8.6.3 inclusive and will provide any information reasonably requested by the Employer in support of such compliance;

- 8.6.6	it shall maintain adequate records to assist in verifying its compliance with the provisions of this clause 8.6 (including without limitation books of account showing all payments made by the Contractor in connection with this Contract) and shall permit the Employer and its third party representatives, on reasonable notice during normal business hours, but without notice in the case of any reasonably suspected breach of clauses 8.6.1 to 8.6.3 inclusive, to access and take copies of such records and to meet with the Contractor's personnel to audit the Contractor's compliance with its obligations under this clause 8.6.  The Contractor shall give all necessary assistance to the conduct of such audits."

Clause 8.6A

Insert new clause 8.6A:

"8.6A.1	Audit access by any third party representative of the Employer in accordance with clause 8.6.6 shall be subject to such representative agreeing to be bound by confidentiality obligations equivalent to those in clause 2.7.6. in respect of the information obtained provided that all information obtained may be disclosed to the Employer.

8.6A.2	The Contractor shall indemnify the Employer against any losses, liabilities, damages, costs (including but not limited to legal fees) and expenses incurred by, or awarded against, the Employer as a result of any breach of clause 8.6 by the Contractor or any breach of provisions equivalent to clause 8.6 in any contract with a sub-consultant or sub-contractor."

Clause 8.6B

Insert new clause 8.6B:

"The Employer may by notice to the Contractor terminate the Contractor's employment under this Contract and (if applicable) any other contract between the Employer and the Contractor:

8.6B.1	in the event of breach of clauses 8.6.1 to 8.6.4 inclusive; and/or

8.6B.2	if an Associated Person (or anyone employed by or acting on behalf of them) engages or has engaged in Corrupt Activity or any activity, practice or conduct which could or would place the Employer in breach of section 7(1) Bribery Act or sections 45(1) or 46(1) Criminal Finances Act; and/or

8.6B.3	where the Employer is a local authority if the Contractor gives or has given any fee or reward the receipt of which is an offence under section 117(2) Local Government Act 1972."

Clause 8.7

In line 1 delete "8.6" and insert "8.6B"

Clause 8.7.2.2

Delete clause 8.7.2.2 and insert:

"provide the Employer (within 10 Business Days) with copies of all the Contractor's Design Documents then prepared whether or not previously provided including without limitation all such documents referred to in clause 2.37 which have been prepared before the date of determination (whether in the course of preparation or completed);"

Clause 8.7.5

Insert at end of clause "provided that if the Employer procures the completion of the outstanding Works for less than the Employer would have had to pay the Contractor to complete the outstanding Works, then for the purposes of clause 8.7.4 the Employer shall be deemed to have paid the same amount to procure the completion of the outstanding Works under clause 8.7.1 as the Employer would have had to pay the Contractor to complete the outstanding Works under this Contract."

Clause 8.9.1.2

Delete clause 8.9.1.2 and insert "Not used."

Clause 8.10.1

In line 1 after "notice to the Employer" insert "or the Employer may by notice to the Contractor".

Clause 8.10.3

Insert at end of clause "and an extension of time for completion shall be given under clause 2.25 equal to the period of suspension"

Clause 8.11.3

In line 3 delete "or 73(1)(c)"

Clause 8.13

Insert new clause 8.13:

"Upon any determination of the Contractor's employment under this section 8 or if this Contract is determined, repudiated or discharged in any other manner and notwithstanding that the validity of such determination, repudiation or discharge may be disputed by the Contractor, the Contractor shall immediately deliver to the Employer possession of the site."

insert as a new Section 10

"Section 10 Compliance with  Modern Slavery Legislation

- Modern Slavery Legislation

  - The Contractor undertakes to the Employer that:

    - it has not and its current and former directors, officers and employees have not and shall not engage in activity which would amount to a breach of the Modern Slavery Legislation or activity which would constitute an offence under the Modern Slavery Legislation if the conduct took place in the United Kingdom;

    - it has not and its current and former directors, officers and employees have not and shall not engage in any activity, practice or conduct which could or would place the Employer in breach of the Modern Slavery Legislation or activity which would constitute an offence under the Modern Slavery Legislation if the conduct took place in the United Kingdom;

    - it has and shall maintain and implement:

      - procedures to ensure compliance with the Modern Slavery Legislation; and

      - adequate procedures designed to prevent conduct that would give rise to an offence under the Modern Slavery Legislation;

    - it shall include undertakings similar to those contained in these clauses 10.1 and 10.2 in any contract it may enter into with sub-consultants and/or sub-contractors and provisions similar to those contained in clauses 10.3 and 10.4;

    - from time to time, at the reasonable request of the Employer, it will confirm in writing that it has complied with its undertakings under clause 10.1 and will provide any information reasonably requested by the Employer in support of such compliance.

  - The Contractor shall maintain adequate records to assist in verifying its compliance with the provisions of this clause 10 and shall permit the Employer and its third party representatives, immediately upon request during normal business hours to access and take copies of such records and to meet with the Contractor's personnel to audit the Contractor's compliance with its obligations under this clause 10.  The Contractor shall give all necessary assistance to the conduct of such audits.

  - Audit access by any third party representative of the Employer in accordance with clause 10.2 shall be subject to such representative agreeing to be bound by confidentiality obligations equivalent to those in clause 2.7.6 in respect of the information obtained provided that all information obtained may be disclosed to the  Employer.

  - In the event of breach of clauses 10.1.1, 10.1.2 or 10.1.3 by the Contractor and/or breach by any sub-consultant or sub-contractor of equivalent clauses required under clause 10.1.4 and/or if the Contractor, sub-consultant or sub-contractor is convicted of an offence under the Modern Slavery Legislation in relation to this Contract or any other contract (whether or not the Employer is a party to that contract), the Parties agree that the Employer may at its sole discretion terminate the Contractor's employment under:

    - this Contract and the provisions of clause 8.7  shall apply; and

    - (if applicable) any other contract between the Parties (whether in relation to the Works or otherwise) and any such termination shall be deemed to be termination for default by the Contractor.

  - The Contractor further undertakes to the Employer that:

    - If required by law to do so, it  shall, for each and every  financial year of the Contractor, comply with its obligations under S.54 of the Modern Slavery Act by publishing a Human Trafficking Statement;

    - It shall include an undertaking similar to that contained in this clause 10.5 in any contract it may enter into with sub-consultants, sub-contractors and/or suppliers.

  - In the event of breach of clauses 10.1.4, 10.1.5, 10.2 and/or 10.5, the Parties agree that the Employer may by notice in writing to the Contractor require that such breaches will be rectified within 7 days of receipt. If the Contractor fails to rectify such breaches in accordance with the notice the Employer may in its sole discretion terminate the Contractor's employment under:

    - this Contract and the provisions of clause 8.7 shall apply; and

    - (if applicable) any other contract between the Parties (whether in relation to the Works or otherwise) and any such termination shall be deemed to be termination for Contractor default.

  - The Contractor shall indemnify the Employer against any losses, liabilities, damages, costs (including but not limited to legal fees) and expenses incurred by, or awarded against, the Employer as a result of:

    - any breach of clauses 10.1, 10.2 or 10.5 by the Contractor;

    - any breach of provisions equivalent to clauses 10.1, 10.2 or 10.5  in any contract with a sub-consultant or sub-contractor; or

    - any act or omission by a sub-consultant or sub-contractor which would have amounted to a breach of the relevant sub-contract had the Contractor complied with its undertaking set out in  clause 10.1.4."

Schedule 1 –Design Submission Procedure

Paragraph 2

In line 1 delete both references to "14 days" and replace with "10 Business Days"

Paragraph 7

In line 2 delete "7 days" and insert "5 Business Days"

In line 5 delete "7 days" and insert "5 Business Days"

Paragraph 9

Insert new paragraph:

"If the Contractor shall find errors in or require any alteration to the Contractor's Design Documents after they have been returned marked by the Employer with either 'A' or 'B' he shall notwithstanding that the errors have become part of the design of the Works resubmit such Contractor's Design Documents together with his corrections to the Employer for comment in accordance with paragraph 1."

Schedule 2 – Supplemental Provisions

Part 2

[Paragraph 7 – cost savings and value improvements

In line 1 of paragraph 7.1 delete "is encouraged to" and insert "shall, when it is reasonably practicable to do so,"

In line 3 of paragraph 7.2 before "." insert "together with such information as the Employer may reasonably request"

Delete paragraph 7.3 and insert:

"7.3.1	The Employer shall consider any proposal submitted pursuant to paragraph 7.2 and if the Employer wishes to accept any such proposal shall seek to agree it with the Contractor [within [  ] Business Days of receipt of the same].  Upon agreement the Employer shall issue an instruction (which for the avoidance of doubt shall not be treated as a Change) confirming the change, the amount of any adjustment of the Contract Sum together with the share of the financial benefit to be paid to the Contractor and any adjustment to the Completion Date.

7.3.2	If a proposal is not accepted a fair and reasonable amount shall be added to the Contract Sum in respect of the cost of its preparation provided that it has been prepared on a fair and reasonable basis."]

[Paragraph 8 – sustainable development and environmental considerations

In line 1 of paragraph 8.1 delete "is encouraged to" and insert "shall"]

[Paragraph 9 – performance indicators and monitoring

Delete paragraph 9.1 and insert:

"The Contractor shall achieve the performance indicators and shall take all practicable steps to ensure that its sub-contractors, suppliers and sub-consultants are subject to the performance indicators.  The Employer shall monitor and assess the Contractor's performance by reference to the performance indicators."

[Paragraph 10 - notification and negotiation of disputes

In line 1 of paragraph 10 delete "With" and insert "The Parties shall each notify the other as soon as they are aware of any matter adversely affecting this Contract or either Party's performance of it.  Such notice shall include proposals for avoiding or mitigating such matter.  In addition with"

Schedule 5 - Third Party Rights

[Delete parts 1 and 2 of schedule 5 and insert "Not used."]

or

[Delete parts 1 and 2 of Schedule 5 and insert:

P&T Rights

(referred to in clauses 1.6 and 7A)

- Duty of care

  - The Contractor warrants and undertakes to the Purchaser or Tenant that:

    - it has performed and shall continue to perform all of its duties and obligations under or arising out of this Contract; and

    - the design of the Works has been and will be carried out using all the reasonable skill and care to be expected of a properly qualified and competent [designer of the relevant discipline] [design and build contractor] experienced in the carrying out of such work for projects of a similar size scope value character and complexity to the Works; and

    - it shall owe a duty of care to the Purchaser or Tenant in respect of all matters which lie within the scope of the Contractor's responsibilities in relation to the Works; and

    - the Purchaser or Tenant shall be deemed to have relied and shall continue to rely upon the Contractor's skill and judgement in respect of all matters which lie within the scope of the Contractor's responsibilities in relation to the Works.

  - The Contractor shall have no duty or obligation under paragraph 1.1 of this schedule that is greater or of longer duration than it would have had and shall be entitled in any action or proceedings by the Purchaser or Tenant to raise equivalent rights in defence of liability (except for set-off or counterclaim) if in lieu of this schedule the Purchaser or Tenant had been a party to the Contract as joint employer.

- Prohibited materials

  - Without prejudice to the generality of paragraph 1 of this schedule the Contractor warrants that it has not used and shall not use and has exercised and shall continue to exercise the standard of skill and care required by paragraph 1.1 of this schedule to ensure that it has not and shall not specify, authorise, cause or allow to be used in the Works any products or materials which:

    - do not conform with UK Designated Standards (where appropriate) or Codes of Practice (or where no such standard exists do not conform with a British Board of Agrément Certificate); and/or

    - are generally known to the construction industry to be deleterious, in the particular circumstances in which they are specified for use, to health and safety and/or the durability of buildings or structures; and/or

    - do not comply with the guidance set out in "Good Practice in the Selection of Construction Materials 2011" published by the British Council for Offices; and/or

    - are specifically prohibited under this Contract.

  - The Contractor will as soon as reasonably practicable notify the Purchaser or Tenant if it becomes aware of any proposed or actual specification and/or use in the Works of any materials which do not comply with paragraph 2.1 of this schedule.

- Copyright and Moral Rights

  - The Contractor grants to the Purchaser or Tenant an irrevocable, royalty-free, non-exclusive licence to use, copy and reproduce the Contractor's Design Documents for any purpose whatsoever connected with the Works and/or the site including but without limitation the execution, completion, extension, maintenance, letting, management, sale, advertisement, alteration, reinstatement and repair of the Works and/or the site provided always that the Contractor shall not be liable for any such use by the Purchaser or Tenant of the Contractor's Design Documents for any purpose other than that for which the same were prepared and provided by the Contractor.

  - The licence referred to in paragraph 3.1 of this schedule carries the right to grant sub-licences, shall be transferable to third parties and shall continue in force notwithstanding any termination of this Contract and/or the Contractor's employment under it.

  - The Contractor warrants that the use of the Contractor's Design Documents for the purposes of the Works and/or pursuant to the licence granted pursuant to paragraph 3.1 of this schedule shall not infringe the rights of any third party.

  - The Contractor waives absolutely all Moral Rights the Contractor may have in the Contractor's Design Documents and/or the Works and where it is not the author shall procure a waiver from the author of any Moral Rights the author may have in respect of the Contractor's Design Documents and/or the Works.

  - When requested to do so by the Purchaser or Tenant the Contractor shall provide to the Purchaser or Tenant copies of the Contractor's Design Documents subject to the Purchaser or Tenant paying the Contractor's reasonable copying charges in connection with complying with such request.

- Insurance

  - The Contractor shall effect and maintain professional indemnity insurance in the sum of [   ] pounds (£[      ]) [for each and every claim] [for each occurrence or series of occurrences arising out of each and every event] [in the aggregate for each year of insurance] [provided that such limit of indemnity may be [in the aggregate for each year of insurance] [[     ] pounds (£[   ]) in respect of claims for pollution and contamination] without unusual or onerous conditions or excesses with reputable insurers carrying on business in the UK with effect from the date of commencement of the Works and for a period expiring no earlier than 12 years from practical completion provided that such insurance remains available to organisations of equivalent size and type to the Contractor's business at commercially reasonable rates and on commercially reasonable terms.

  - The Contractor undertakes to provide to the Purchaser or Tenant on demand from time to time such evidence as the Purchaser or Tenant may reasonably require to satisfy himself that the insurance required by paragraph 4.1 of this schedule is being maintained.

  - The Contractor shall inform the Purchaser or Tenant if the insurance required by paragraph 4.1 of this schedule is not maintained or renewed or for any reason becomes void or unenforceable or ceases to be available at commercially reasonable rates and terms and shall agree with the Purchaser or Tenant the best means of protecting the Contractor and the Purchaser or Tenant's respective interests and carry out such actions as shall be necessary to implement any agreed actions.

  - The Contractor shall not compromise, settle or waive any insurance claim it may have relating to any liability under this schedule of rights without the Purchaser or Tenant's prior consent provided that nothing in this paragraph shall prevent the Contractor's insurers from taking over (in the Contractor's name) the defence of any claim made by the Purchaser or Tenant under this schedule of rights and (in that capacity) from conducting and settling it as they see fit.

- Assignment

  - The Contractor may not without the consent of the Purchaser or Tenant assign its rights under this schedule of rights.

  - The Purchaser or Tenant may (without the consent of the Contractor) assign the benefit of this schedule of rights and/or its rights under this schedule:

    - to any mortgagee and by way of re-assignment on redemption;

    - to any subsidiary or holding company or the Purchaser or Tenant or another subsidiary or holding company of such company as subsidiary or holding company are defined in section 1149 Companies Act 2006;

    - on two other occasions only.

  - In this schedule references to the Purchaser or Tenant shall include where the context admits its permitted assignees but not so as to permit more than two assignments under paragraph 5.2.3 of this schedule.

  - The Contractor undertakes with the Purchaser or Tenant not to contend that any person to whom the benefit of this schedule may be assigned will be precluded from recovering under this schedule any loss resulting from any breach of this schedule either by reason that the person is an assignee and not the original recipient of this schedule of rights or by reason that the Purchaser or Tenant or any intermediate owner of the Purchaser or Tenant's interest in the Works shall escape loss resulting from such breach by reason of the disposal of its interest in the Works.

- Delay

The Contractor shall not be liable to the Purchaser or Tenant in respect of any delay to the completion of the Works.

- Notices

  - Any notice to be given under this schedule shall be in writing and shall be deemed to be duly given if it is delivered to the parties' registered office for the time being.

  - Notices shall be delivered by:

    - hand delivery; or

    - pre-paid registered or recorded delivery mail.

  - Notices and communications shall be deemed to have been delivered or received in the case of:

    - hand delivery on the date of delivery;

    - pre-paid registered or recorded delivery mail on the second Business Day after the notice of communication is posted.

- Continuing effect

Notwithstanding the completion of the Works or any part of the Works this schedule shall continue to have effect.

- Miscellaneous

  - Nothing in this schedule shall limit or affect any other rights or remedies (whether under any contract, at law, at equity or otherwise) which the Purchaser or Tenant would have against the Contractor in the absence of this schedule.

  - The Contractor's liability under this schedule shall not be released, diminished or in any other way affected by:

    - the appointment by the Purchaser or Tenant of any person to survey the site or to monitor the carrying out of the Works or to inspect any documents relating to the site and/or the Works on behalf of the Purchaser or Tenant or the failure to appoint such a person; or

    - any approval or consent given or withheld or purported to be given or withheld by or on behalf of the Purchaser or Tenant.

- Law

This schedule and any dispute or claim arising out of or in connection with it or its subject matter or formation (including non-contractual disputes or claims) shall be governed by and construed in accordance with the laws of England and Wales and the parties hereby submit to the exclusive jurisdiction of the English courts.

[Schedule 5A

Insert new Schedule 5A as follows:

Funder Rights

(referred to in clauses 1.6 and 7B)

- Duty of care

  - The Contractor warrants and undertakes to the Funder that:

    - it has performed and shall continue to perform all of its duties and obligations under or arising out of this Contract; and

    - the design of the Works has been and will be carried out with all the reasonable skill and care to be expected of a properly qualified and competent [designer of the relevant discipline] [design and build contractor] experienced in the carrying out of such work for projects of a similar size scope value character and complexity to the Works; and

    - it shall owe a duty of care to the Funder in respect of all matters which lie within the scope of the Contractor's responsibilities in relation to the Works; and

    - the Funder shall be deemed to have relied and shall continue to rely upon the Contractor's skill and judgement in respect of all matters which lie within the scope of the Contractor's responsibilities in relation to the Works.

  - The Contractor shall have no duty or obligation under paragraph 1.1 of this schedule that is greater or of longer duration than it would have had and shall be entitled in any action or proceedings by the Funder to raise equivalent rights in defence of liability (except for set-off or counterclaim) if in lieu of this schedule the Funder had been a party to the Contract as joint employer.

- Prohibited materials

  - Without prejudice to the generality of paragraph 1 of this schedule the Contractor warrants that it has not used and shall not use and has exercised and shall continue to exercise the standard of skill and care required by paragraph 1.1 of this schedule to ensure that it has not and shall not specify, authorise, cause or allow to be used in the Works any products or materials which:

    - do not conform with UK Designated Standards (where appropriate) or Codes of Practice (or where no such standard exists do not conform with a British Board of Agrément Certificate); and/or

    - are generally known to the construction industry to be deleterious, in the particular circumstances in which they are specified for use, to health and safety and/or the durability of buildings or structures; and/or

    - do not comply with the guidance set out in "Good Practice in the Selection of Construction Materials 2011" published by the British Council for Offices; and/or

    - are specifically prohibited under this Contract.

  - The Contractor shall as soon as reasonably practicable notify the Funder if it becomes aware of any proposed or actual specification and/or use in the Works of any materials which do not comply with paragraph 2.1 of this schedule.

- Copyright and moral rights

  - The Contractor grants to the Funder an irrevocable, royalty-free, non-exclusive licence to use, copy and reproduce the Contractor's Design Documents for any purpose whatsoever connected with the Works and/or the site including but without limitation the execution, completion, extension, maintenance, letting, management, sale, advertisement, alteration, reinstatement and repair of the Works and/or the site provided always that the Contractor shall not be liable for any such use by the Funder of the Contractor's Design Documents for any purpose other than that for which the same were prepared and provided by the Contractor.

  - The licence referred to in paragraph 3.1 of this schedule carries the right to grant sub-licences, shall be transferable to third parties and shall continue in force notwithstanding any termination of this appointment and/or the Contractor's employment under it.

  - The Contractor warrants that the use of the Contractor's Design Documents for the purposes of the Works and/or pursuant to the licence granted pursuant to paragraph 3.1 of this schedule shall not infringe the rights of any third party.

  - The Contractor waives absolutely all Moral Rights the Contractor may have in the Contractor's Design Documents and/or the Works and where it is not the author shall procure a waiver from the author of any Moral Rights the author may have in respect of the Contractor's Design Documents and/or the Works.

  - When requested to do so by the Funder the Contractor shall provide to the Funder copies of the Contractor's Design Documents subject to the Funder paying the Contractor's reasonable copying charges in connection with complying with such request.

- Step-in

  - The Contractor covenants with the Funder that if any event of default shall occur under the agreement between the Funder and the Employer in relation to the Works at any time the Contractor shall, if so required by notice in writing given by the Funder and, subject to paragraph 14.5 of this schedule, accept the instructions of the Funder or its appointee to the exclusion of the Employer upon the terms and conditions of this Contract and the Employer acknowledges that the Contractor shall be entitled to rely on the notice given to the Contractor by the Funder as conclusive evidence for the purpose of this schedule that circumstances have occurred permitting the Funder to give such notice.

  - The Contractor hereby covenants that it shall not exercise nor seek to exercise any right to terminate or treat as terminated this Contract and/or its employment or discontinue or suspend the performance of any of its obligations under this Contract without first giving to the Funder prior written notice specifying the Contractor's ground for terminating or treating as terminated this Contract and/or its employment and/or discontinuing or suspending its performance under this Contract.  If the grounds are that sums which are due have not been paid by the final payment date and no effective pay less notice has been given the Contractor shall give 7 days notice otherwise the Contractor shall give 15 Business Days notice.

  - Compliance by the Contractor with the provisions of paragraph 4.2 of this schedule shall not be treated as a waiver of any breach on the part of the Employer giving rise to the right of determination, discontinuance or suspension nor otherwise prevent the Contractor from exercising its rights after the expiration of the notice unless the right of determination discontinuance or suspension shall have ceased pursuant to the provision of paragraph  4.4 of this schedule.

  - Within the relevant notice period referred to in paragraph 4.2 of this schedule the Funder or their appointee may give written notice to the Contractor, subject to paragraph 4.5 of this schedule, requiring the Contractor to continue with the performance of its duties and obligations under this Contract.

  - It shall be a condition of any notice given by the Funder under paragraph 4.1 or paragraph 4.4 of this schedule that the Funder or their appointee:

    - acknowledges that they assume all the obligations of the Employer;

    - undertakes unconditionally to the Contractor to pay to the Contractor within 15 Business Days after the date of the notice under paragraph 4.1 or paragraph 4.4 of this schedule any sums which have become properly due and payable to the Contractor under this Contract but which are at the date of such notice unpaid and in the case of a notice from an appointee of the Funder, the Funder shall guarantee all payments due to the Contractor from the appointee.

  - In the event of the Funder or their appointee giving notice to the Contractor in accordance with paragraph 4.1 or paragraph 4.4 of this schedule this Contract shall continue in full force and effect and in all respects as if this Contract had been made between the Contractor and the Funder or their appointee (as applicable) to the exclusion of the Employer (but without prejudice to any rights of recovery as between the Contractor and the Employer) and the provisions of this paragraph shall apply notwithstanding any dispute or doubt as to the validity of such rights of determination or discontinuance.

  - The Employer confirms its agreement to the terms and conditions of this schedule and its concurrence with the arrangements made and contemplated by this schedule.

- Insurance

  - The Contractor shall effect and maintain professional indemnity insurance in the sum of [    ] pounds (£ [    ]) [for each and every claim] [for each occurrence of series of occurrences arising out of each and every event] [provided that such limit of indemnity may be [in the aggregate for each year of insurance] [[    ] pounds (£ [    ])] in respect of claims for pollution or contamination] without unusual or onerous conditions or excesses with reputable insurers carrying on business in the UK with effect from the date of commencement of the Works and for a period expiring no earlier than 12 years from practical completion provided that such insurance remains available to organisations of equivalent size and type to the Contractor's business at commercially reasonable rates and on commercially reasonable terms.

  - The Contractor undertakes to provide to the Funder on demand from time to time such evidence as the Funder may reasonably require to satisfy himself that the insurance required by paragraph 5.1 of this schedule is being maintained.

  - The Contractor shall inform the Funder if the insurance required by paragraph 5.1 of this schedule is not maintained or renewed or for any reason becomes void or unenforceable or ceases to be available at commercially reasonable rates and terms and shall agree with the Funder the best means of protecting the Contractor and the Funder's respective interests and carry out such actions as shall be necessary to implement any agreed actions.

  - The Contractor shall not compromise settle or waive any insurance claim it may have relating to any liability under this schedule without the Funder's prior consent provided that nothing in this paragraph shall prevent the Contractor's insurers from taking over (in the Contractor's name) the defence of any claim made by the Funder under this schedule of rights and (in that capacity) from conducting and settling it as they see fit.

- Assignment

  - The Contractor shall not without the consent of the Funder assign its rights under this schedule.

  - The Funder may (without the consent of the Contractor) assign the benefit of this schedule and/or its rights under this schedule:

    - to any subsidiary or holding company of the Funder or another subsidiary or holding company of such company as subsidiary or holding company are defined in section 1159 Companies Act 2006;

    - on two other occasions only.

  - In this schedule references to Funder shall include where the context admits its permitted assignees but not so as to permit more than two assignments under paragraph 6.2.2 of this schedule.

  - The Contractor undertakes with the Funder not to contend that any person to whom the benefit of this schedule may be assigned will be precluded from recovering under this schedule any loss resulting from any breach of this schedule either by reason that the person is an assignee and not the original recipient of this schedule or by reason that the Funder or any intermediate owner of the Funder's interest in the Works shall escape loss resulting from such breach by reason of the disposal of its interest in the Works.

- Notices

  - Any notice to be given under this schedule shall be in writing and shall be deemed to be duly given if it is delivered to the parties' registered office for the time being.

  - Notices shall be delivered by:

    - hand; or

    - pre-paid registered or recorded delivery mail.

  - Notices and communications shall be deemed to have been delivered or received in the case of:

    - hand delivery on the date of delivery;

    - pre-paid registered or recorded delivery mail on the second Business Day after the notice of communication is posted.

- Continuing effect

Notwithstanding the completion of the Works or any part of the Works this schedule shall continue to have effect.

- Miscellaneous

  - Nothing in this schedule shall limit or affect any other rights or remedies (whether under any contract, at law, at equity or otherwise) which the Funder would have against the Contractor in the absence of this schedule.

  - The Contractor's liability under this schedule shall not be released, diminished or in any other way affected by:

    - the appointment by the Funder of any person to survey the site or to monitor the carrying out of the Works or to inspect any documents relating to the site and/or the Works on behalf of the Funder or the failure to appoint such a person; or

    - any approval or consent given or withheld or purported to be given or withheld by or on behalf of the Funder.

- Law

This schedule and any dispute or claim arising out of or in connection with it or its subject matter or formation (including non-contractual disputes or claims) shall be governed by and construed in accordance with the laws of England and Wales and the parties hereby submit to the exclusive jurisdiction of the English courts."

Schedule 6 – forms of bond

[Part 1 – advance payment bond

In paragraph 3.2 delete final sentence.

Delete paragraph 8 and insert "The Bond and the benefit of the Bond shall be capable of being assigned by the Employer without the consent of the Surety to a party to whom the benefit of the Contract has been assigned.  The Surety shall not assign the Bond or the benefit of the Bond."

At the start of paragraph 9 delete "Notwithstanding" and insert "Subject to paragraph 8, notwithstanding"

In Schedule to advance payment bond delete "The above signatures to be authenticated by the Employer's Bankers"]

[Part 2 – payment for off-site materials and/or goods

In paragraph 4 delete final sentence.

Delete paragraph 10 and insert "The Bond and the benefit of the Bond shall be capable of being assigned by the Employer without the consent of the Surety to a party to whom the benefit of the Contract has been assigned.   The Surety shall not assign the Bond or the benefit of the Bond."

At the start of paragraph 11 delete "Notwithstanding" and insert "Subject to paragraph 10, notwithstanding"

In Schedule to bond for payment for off-site materials and/or goods delete "The above signatures to be authenticated by the Employer's Bankers"]

[Part 3 – retention bond

In paragraph 4.1 delete ", and with the signature(s) therein authenticated by the Employer's bankers"

[Delete paragraph 4.3 and insert "Not used."]

[Delete paragraph 4.4 and insert "Not used."]

Delete paragraph 5 and insert "The Bond and the benefit of the Bond shall be capable of being assigned by the Employer without the consent of the Surety to a party to whom the benefit of the Contract has been assigned.  The Surety shall not assign the Bond or the benefit of the Bond."

At the start of paragraph 8 delete "Notwithstanding" and insert "Subject to paragraph 5, notwithstanding"]

Schedule 7 – Fluctuations

Delete schedule 7 and insert "Not used."

Appendix 2

Bond

(referred to in clause 7)

Appendix 3

Parent Company Guarantee

(referred to in clause 7)

[Appendix 4

Deed of Novation

(referred to in clause 3.17)]

Appendix 5

Contractor Warranties

(referred to in clause 7C)

- Contractor warranty to Purchaser and/or Tenant

- Contractor warranty to Funder

Part 1

Contractor warranty to Purchaser and/or Tenant

Part 2

Contractor warranty to Funder

Appendix 6

Sub-Contractor Warranties

(referred to in clause 7E)

- Sub-Contractor warranty to Employer

- Sub-Contractor warranty to Purchaser and/or Tenant

- Sub-Contractor warranty to Funder

Appendix 7

Sub-Consultant [and Novated Consultant] Warranties

(referred to in clause 7E)

- [Novated Consultant or] Sub-Consultant warranty to Employer

- [Novated Consultant or] Sub-Consultant warranty to Funder

- [Novated Consultant or] Sub-Consultant warranty to Purchaser and/or Tenant

Appendix 8

Nominating Notice

| To: | [ ] (registration number [ ]) [of] [whose registered office is at] [ ] |
| --- | --- |
| From: | Trowers & Hamlins LLP of 3 Bunhill Row, London, EC1Y 8YZ for and on behalf of [ ] (registration number [ ]) [of] [whose registered office is at] [ ] (the Employer) |
| Date: | [ ] |

Dear Sirs

[                                                                            ] (the Project)

You have entered into a building contract with the Employer dated [           ] in respect of the Project (the Building Contract).

Schedule [5] [5A] of the Building Contract (the Schedule) sets out in the benefits and rights which may be enforced by a third party on the issue of this notice.  On behalf of the Employer we hereby nominate [                ] (registration number [        ]) [of] [whose registered office is at] [                      ] as a third party (the Third Party) entitled to enforce the benefits and rights set out in appendix [   ] in accordance with the terms of the Building Contract as from the date of this notice.

[The Third Party has taken or agreed to take a lease of the premises known as [         ] forming part of the Project.]  [The Third Party has agreed to purchase the whole of the property of which the Project forms part.] [The Third Party has agreed to provide funding to complete the Project.]

[The rights of the Third Party set out in paragraph [    ] of the Schedule shall have priority over the rights of [    ] set out in paragraph [   ] of the Schedule whether such rights are exercised by the Third Party before or after the exercise by [	] of its rights.]

Yours faithfully

cc  Third Party

[Appendix 9

Anti-corruption Policy

(referred to in clause 8.6)]